## Construction
Name | Project Number | Project Manager | Program Manager | Work Package Status | Location | Region | CS Contact | Constructability Review Completed | Overall Committed Hrs | Overall Start Date Placeholder | Overall Start Date Original Planned | Overall Completion Date Placeholder | Overall Completion Date Original Planned | Overall Start Date Forecast | Overall Start Date Actual | Overall Completion Date Forecast | Overall Completion Date Actual | Original Cost Estimate | Forecast At Completion | Cost At Completion | Dpt 1 Department | Dpt 1 Start Date Placeholder | Dpt 1 End Date Placeholder | Dpt 1 Start Date Original Planned | Dpt 1 End Date Original Planned | Dpt 1 Start Date Forecast | Dpt 1 End Date Forecast | Dpt 1 Start Date Actual | Dpt 1 End Date Actual | Dpt 1 Original Cost Estimate | Dpt 1 Forecast At Completion | Dpt 1 Cost At Completion | Dpt 1 Committed Hrs | Dpt 2 Department | Dpt 2 Start Date Placeholder | Dpt 2 End Date Placeholder | Dpt 2 Start Date Original Planned | Dpt 2 End Date Original Planned | Dpt 2 Start Date Forecast | Dpt 2 End Date Forecast | Dpt 2 End Date Actual | Dpt 2 Start Date Actual | Dpt 2 Original Cost Estimate | Dpt 2 Forecast At Completion | Dpt 2 Cost At Completion | Dpt 2 Committed Hrs | Dpt 3 Department | Dpt 3 Start Date Placeholder | Dpt 3 End Date Placeholder | Dpt 3 Start Date Original Planned | Dpt 3 End Date Original Planned | Dpt 3 Start Date Forecast | Dpt 3 End Date Forecast | Dpt 3 Start Date Actual | Dpt 3 End Date Actual | Dpt 3 Original Cost Estimate | Dpt 3 Forecast At Completion | Dpt 3 Cost At Completion | Dpt 3 Committed Hrs | Dpt 4 Department | Dpt 4 Start Date Placeholder | Dpt 4 End Date Placeholder | Dpt 4 Start Date Original Planned | Dpt 4 End Date Original Planned | Dpt 4 Start Date Forecast | Dpt 4 End Date Forecast | Dpt 4 Start Date Actual | Dpt 4 End Date Actual | Dpt 4 Original Cost Estimate | Dpt 4 Forecast At Completion | Dpt 4 Cost At Completion | Dpt 4 Committed Hrs
Project Name 1 | Project Number1 | Project Manager1 | Program Manager1 | Construction | Location1 | NI | Contact1 | FALSE | 1150 | 2019-04-01 | 2019-04-08 | 2019-05-15 | 2019-05-10 | 2019-04-07 | 2019-04-07 | 2019-05-31 |  | 120199 | 120199 |  | NI Elect
Project Name 2 | Project Number2 | Project Manager2 | Program Manager2 | Construction | Location2 | VI | Contact2 | TRUE |  | 2019-02-04 | 2019-01-15 | 2019-07-05 | 2019-07-05 | 2019-01-15 | 2019-02-19 | 2019-09-01 |  | 1243284 | 1296777 |  | VI Line |  |  | 2019-04-29 | 2019-05-05 | 2019-04-29 | 2019-07-30 |  |  | 953373 | 1017921 |  | 3322 | VI Civil |  |  | 2019-02-04 | 2019-05-31 | 2019-02-04 | 2019-05-31 |  | 2019-02-19 | 256941 | 278856 |  | 817
Project Name 3 | Project Number3 | Project Manager3 | Program Manager3 | Construction | Location3 | SI | Contact3 | TRUE | 618 | 2018-10-01 | 2018-10-01 |  | 2018-11-01 | 2018-10-09 | 2018-10-09 |  | 2018-11-01 | 72992 | 72203 | 60523
Project Name 4 | Project Number4 | Project Manager4 | Program Manager4 | Pre-Construction | Location4 | SI | Contact4 | FALSE |  | 2019-05-31 |  | 2019-09-30 | [8 empty] | SI Civil | 2019-05-31 | 2019-06-21 | [10 empty] | SI Elect | 2019-06-21 | 2019-09-06 | [10 empty] | SI Civil | 2019-09-09 | 2019-09-30
Project Name 5 | Project Number5 | Project Manager5 | Program Manager5 | Pre-Construction | Location5 | NI | Contact5 | FALSE | 1650 | 2019-09-16 |  | 2019-10-11 | [8 empty] | NI Line
Project Name 6 | Project Number6 | Project Manager6 | Program Manager6 | Cancelled | Location6 | NI | Contact6 | FALSE | 726 | 2019-06-03 |  | 2019-06-14 | [8 empty] | NI Line
Project Name 7 | Project Number7 | Project Manager7 | Program Manager7 | Construction | Location7 | LM | Contact7 | TRUE | 3369 |  | 2018-08-13 |  | 2018-10-15 |  | 2018-10-17 | 2019-08-30 |  | 365000 | 544409 |  | LM Elect1 |  |  | 2018-08-13 | 2018-10-15 | 2018-08-13 | 2019-08-30 | 2018-10-17 |  | 125940 | 157837 |  | 882 | LM Civil |  |  | 2018-08-13 | 2018-10-15 | 2019-04-01 | 2019-08-30 |  | 2019-04-08 | 0 | 0 |  | 1508 | LM Field Mech |  |  | 2018-08-13 | 2018-10-15 | 2019-04-01 | 2019-08-30 | 2019-04-08 |  | 237707 | 386570 |  | 979
Project Name 8 | Project Number8 | Project Manager8 | Program Manager8 | Pre-Construction | Location8 | LM | Contact8 | FALSE | 500 | 2019-11-01 |  | 2019-12-20 | [8 empty] | LM Elect1
Project Name 9 | Project Number9 | Project Manager9 | Program Manager9 | Pre-Construction | Location9 | LM | Contact9 | FALSE | 1000 | 2020-03-30 |  | 2020-04-30 | [5 empty] | 101000 |  |  | LM Elect1
Project Name 10 | Project Number10 | Project Manager10 | Program Manager10 | Construction | Location10 | VI | Contact10 | FALSE | 220 | 2019-05-13 | 2019-05-13 | 2019-05-28 | 2019-05-28 | 2019-05-13 | 2019-05-13 | 2019-05-28 |  | 37250 | 37250 |  | VI Civil
Project Name 11 | Project Number11 | Project Manager11 | Program Manager11 | Construction | Location11 | NI | Contact11 | TRUE | 6400 | 2019-03-01 | 2019-03-11 | 2019-10-31 | 2019-10-11 | 2019-03-11 | 2019-03-11 | 2019-10-11 |  | 2516867 | 2644273 |  | NI Civil | 2019-03-01 | 2019-10-31 | 2019-03-11 | 2019-08-28 | 2019-03-11 | 2019-07-26 | 2019-03-11 |  | 1461342 | 1556229 |  | 6400 | NI Elect | 2019-03-01 | 2019-10-31 | 2019-03-11 | 2019-10-11 | 2019-03-11 | 2019-10-11 |  | 2019-03-11 | 1055525 | 1088044 |  | 7000
Project Name 12 | Project Number12 | Project Manager12 | Program Manager12 | Construction | Location12 | NI | Contact12 | FALSE | 1710 | 2018-11-19 | 2018-11-19 | 2019-03-01 | 2019-02-28 | 2018-11-19 | 2018-11-19 | 2019-05-17 |  | 186009 | 195344 |  | NI Civil
Project Name 13 | Project Number13 | Project Manager13 | Program Manager13 | Construction | Location13 | SI | Contact13 | TRUE | 4000 | 2019-02-18 | 2019-02-18 | 2019-09-30 | 2019-09-30 | 2019-04-01 | 2019-04-01 | 2019-09-30 |  | 632000 | 632000 |  | SI Line
Project Name 14 | Project Number14 | Project Manager14 | Program Manager14 | Pre-Construction | Location14 | VI | Contact14 | FALSE | 4734 | 2020-06-09 | [10 empty] | LM Winders
Project Name 15 | Project Number15 | Project Manager15 | Program Manager15 | Construction | Location15 | LM | Contact15 | TRUE |  | 2019-01-01 | 2019-01-07 | 2020-02-13 | 2020-02-15 | 2019-01-14 | 2019-01-07 | 2020-04-29 |  | 6812912 | 6899335 |  | LM Elect2 | 2019-01-14 |  | 2019-01-14 | 2020-02-14 | 2019-01-14 | 2020-03-10 | 2019-01-14 |  | 2850471 | 2850471 |  | 21033 | LM Civil | 2019-01-14 |  | 2019-01-14 | 2019-12-27 | 2019-01-14 | 2020-02-26 |  | 2019-01-14 | 3562807 | 3562807 |  | 17105 | LM Winders | 2019-08-12 |  | 2019-08-12 | 2019-10-17 | 2019-08-12 | 2019-10-17 |  |  | 211674 | 211674 |  | 1520 | LM Field Mech | 2019-10-01 |  | 2019-10-01 | 2020-02-05 | 2019-10-01 | 2020-02-05 |  |  | 187960 | 187960 |  | 872
Project Name 16 | Project Number16 | Project Manager16 | Program Manager16 | Pre-Construction | Location16 | LM | Contact16 | TRUE | 2100 | 2019-06-03 | 2019-05-13 | 2019-09-13 | 2019-10-22 | 2019-05-13 |  | 2019-10-22 |  | 2092065 | 2092065 |  | LM Civil |  |  | 2019-05-13 | 2019-08-16 | 2019-05-13 |  |  |  | 1693166 | 1693166 |  | 4247 | LM Line |  |  | 2019-08-06 | 2019-10-22 | 2019-08-06 |  |  |  | 398899 | 398899 |  | 2100
Project Name 17 | Project Number17 | Project Manager17 | Program Manager17 | Pre-Construction | Location17 | VI | Contact17 | TRUE | 0 |  | 2020-04-01 |  | 2020-12-31 | 2020-02-01 |  |  |  | 0 |  |  | VI Elect
Project Name 18 | Project Number18 | Project Manager18 | Program Manager18 | Pre-Construction | Location18 | VI | Contact18 | FALSE | 0 | 2021-06-01 |  | 2021-12-15 | [5 empty] | 0 |  |  | VI Elect
Project Name 19 | Project Number19 | Project Manager19 | Program Manager19 | Pre-Construction | Location19 | VI | Contact19 | FALSE | 1740 |  | 2018-04-01 |  | 2019-03-01 | 2019-05-13 |  | 2021-12-31 |  | 0 |  |  | VI Elect
Project Name 20 | Project Number20 | Project Manager20 | Program Manager20 | Pre-Construction | Location20 | LM | Contact20 | FALSE | 807 | 2019-02-19 | 2019-02-19 | 2019-03-15 | 2019-03-15 | 2019-02-19 | 2019-02-19 | 2019-03-15 | 2019-03-15 | 98896 | 98896
Project Name 21 | Project Number21 | Project Manager21 | Program Manager21 | Completion | Location21 | SI | Contact21 | TRUE |  |  | 2017-08-01 |  | 2018-06-15 | 2018-02-05 | 2018-03-01 | 2019-05-31 | 2019-05-13 | 1291000 | 1292098
Project Name 22 | Project Number22 | Project Manager22 | Program Manager22 | Completion | Location22 | SI | Contact22 | TRUE | 6000 |  | 2018-06-01 |  | 2018-10-31 |  | 2018-08-01 | 2019-03-31 | 2019-03-14 | 702000 | 700000 |  | SI Line
Project Name 23 | Project Number23 | Project Manager23 | Program Manager23 | Completion | Location23 | NI | Contact23 | TRUE | 750 | 2018-12-10 | 2018-12-10 | 2018-12-17 | 2018-12-17 | 2018-12-10 | 2018-12-06 | 2018-12-17 | 2018-12-17 | 252546 | 309532 |  | NI Civil
Project Name 24 | Project Number24 | Project Manager24 | Program Manager24 | Construction | Location24 | SI | Contact24 | TRUE | 21825 |  | 2018-01-22 |  | 2018-12-31 |  | 2018-01-22 | 2019-05-31 |  | 3228000 | 3421092 |  | SI Elect
Project Name 25 | Project Number25 | Project Manager25 | Program Manager25 | Construction | Location25 | SI | Contact25 | TRUE | 2880 | 2019-02-04 | 2019-02-04 | 2019-05-17 | 2019-05-17 | 2019-02-04 | 2019-02-04 | 2019-05-17 |  | 688471 | 692824 |  | SI MASS (MECH) | 2019-02-04 | 2019-05-17 | 2019-02-04 | 2019-05-17 | 2019-02-04 | 2019-05-17 | 2019-02-04 |  | 650845 | 658566 |  | 2880 | SI Elect | 2019-02-04 | 2019-05-17 | 2019-02-04 | 2019-05-17 | 2019-02-04 | 2019-05-17 |  | 2019-02-04 | 37626 | 34256 |  | 330
Project Name 26 | Project Number26 | Project Manager26 | Program Manager26 | Pre-Construction | Location26 | NI | Contact26 | TRUE | 570 |  | 2018-10-29 |  | 2018-11-09 | 2019-07-02 |  | 2019-07-19 |  | 135000 | 135000 |  | LM Field Mech
Project Name 27 | Project Number27 | Project Manager27 | Program Manager27 | Pre-Construction | Location27 | NI | Contact27 | FALSE | 500 | 2018-10-01 | 2019-09-02 | 2018-12-01 | 2019-09-30 | 2019-09-02 |  | 2019-09-30 |  | 100000 | 100000 |  | LM Field Mech
Project Name 28 | Project Number28 | Project Manager28 | Program Manager28 | Pre-Construction | Location28 | VI | Contact28 | FALSE | 2400 | 2020-06-01 |  | 2020-08-31 | [5 empty] | 750000 | 750000 |  | LM Field Mech
Project Name 29 | Project Number29 | Project Manager29 | Program Manager29 | Pre-Construction | Location29 | VI | Contact29 | FALSE | 810 | 2019-04-01 |  | 2019-04-30 | [5 empty] | 192688 | 192688 |  | LM Field Mech
Project Name 30 | Project Number30 | Project Manager30 | Program Manager30 | Pre-Construction | Location30 | LM | Contact30 | TRUE | 165 | 2019-01-01 |  | 2019-01-31 | [5 empty] | 100000 | 100000 |  | LM Field Mech
Project Name 31 | Project Number31 | Project Manager31 | Program Manager31 | Pre-Construction | Location31 | LM | Contact31 | FALSE | 1200 | 2020-06-01 |  | 2020-08-31
Project Name 32 | Project Number32 | Project Manager32 | Program Manager32 | Pre-Construction | Location32 | LM | Contact32 | FALSE | 2400 | 2020-02-04 |  | 2020-04-26 | [8 empty] | LM Field Mech
Project Name 33 | Project Number33 | Project Manager33 | Program Manager33 | Pre-Construction | Location33 | NI | Contact33 | FALSE | 600 | 2019-10-01 | 2018-10-01 | 2019-10-31 | 2018-10-31 | 2019-10-01 |  | 2019-10-31 |  | 90000 | 90000 |  | LM Field Mech
Project Name 34 | Project Number34 | Project Manager34 | Program Manager34 | Pre-Construction | Location34 | NI | Contact34 | FALSE |  | 2019-06-14 |  | 2020-10-31 | [8 empty] | LM Field Mech | 2019-06-14 | 2020-10-31 | [9 empty] | 2400 | LM Civil | 2019-06-14 | 2020-10-31 | [9 empty] | 2400 | LM Elect2 | 2019-06-14 | 2020-10-31 | [9 empty] | 600
Project Name 35 | Project Number35 | Project Manager35 | Program Manager35 | Pre-Construction | Location35 | LM | Contact35 | FALSE | 700 | 2019-09-17 |  | 2019-10-25 | [8 empty] | LM Civil
Project Name 36 | Project Number36 | Project Manager36 | Program Manager36 | Construction | Location36 | LM | Contact36 | FALSE |  |  | 2018-10-01 |  | 2019-04-01 | 2018-10-01 | 2018-10-01 | 2019-06-14 |  | 474000 | 497373 |  | LM Civil | 2018-10-01 | 2018-10-31 | 2018-10-01 | 2018-10-31 | 2018-10-01 |  | 2018-10-01 | 2018-11-09 | 165000 | 106168 |  | 1000 | LM Elect1 | 2019-01-07 | 2019-04-01 | 2019-01-07 | 2019-03-29 | 2019-01-07 | 2019-06-14 |  | 2019-01-07 | 309000 | 310873 |  | 2050
Project Name 37 | Project Number37 | Project Manager37 | Program Manager37 | Construction | Location37 | LM | Contact37 | FALSE | 3200 |  | 2018-04-20 |  | 2019-07-31 |  | 2018-04-20 | 2019-09-30 |  | 272154 | 325169 |  | LM Elect1
Project Name 38 | Project Number38 | Project Manager38 | Program Manager38 | Construction | Location38 | LM | Contact38 | FALSE | 1800 |  | 2018-09-17 |  | 2018-11-19 |  | 2018-09-17 | 2019-06-28 |  | 174000 | 145416 |  | LM Elect1
Project Name 39 | Project Number39 | Project Manager39 | Program Manager39 | Pre-Construction | Location39 | NI | Contact39 | FALSE | 3500 | 2019-05-15 |  | 2019-07-15 | [5 empty] | 350000 | 350000 |  | NI Line
Project Name 40 | Project Number40 | Project Manager40 | Program Manager40 | Construction | Location40 | LM | Contact40 | FALSE | 650 |  | 2018-08-07 |  | 2019-03-30 |  | 2018-08-07 | 2019-03-30 |  | 58000 |  |  | LM Elect1
Project Name 41 | Project Number41 | Project Manager41 | Program Manager41 | Construction | Location41 | LM | Contact41 | FALSE | 360 | 2018-09-01 | 2018-09-01 | 2019-06-30 | 2019-06-30 | 2018-09-01 | 2018-09-01 | 2019-06-30 |  | 120800 | 100000 |  | LM Elect1
Project Name 42 | Project Number42 | Project Manager42 | Program Manager42 | Construction | Location42 | LM | Contact42 | FALSE | 1300 |  | 2018-09-15 |  | 2019-03-30 |  | 2018-09-15 | 2019-03-30 |  | 128000 | 123630 |  | LM Elect1
Project Name 43 | Project Number43 | Project Manager43 | Program Manager43 | Construction | Location43 | LM | Contact43 | TRUE |  | 2018-07-26 | 2018-07-26 |  | 2018-10-15 | 2018-07-26 | 2018-07-26 | 2019-07-30 |  | 1710000 | 1728206 |  | LM Civil |  |  | 2018-07-26 | 2018-10-09 | 2018-07-26 | 2019-07-30 | 2018-07-26 |  | 1625961 | 1455695 |  | 3750 | LM Line |  |  | 2018-09-20 | 2018-10-15 | 2018-09-20 | 2018-12-14 | 2018-12-14 | 2018-09-20 | 84039 | 72511 |  | 450
Project Name 44 | Project Number44 | Project Manager44 | Program Manager44 | Pre-Construction | Location44 | NI | Contact44 | FALSE | 7200 | 2021-03-01 |  | 2021-10-30 | [8 empty] | NI Elect
Project Name 45 | Project Number45 | Project Manager45 | Program Manager45 | Pre-Construction | Location45 | NI | Contact45 | FALSE |  | 2022-04-11 |  | 2022-11-21 | [5 empty] | 5820000 | 5820000 |  | NI Civil | 2022-04-11 | 2022-08-01 | [9 empty] | 6200 | NI Line | 2022-05-19 | 2022-11-21 | [9 empty] | 18800
Project Name 46 | Project Number46 | Project Manager46 | Program Manager46 | Pre-Construction | Location46 | NI | Contact46 | TRUE | 840 | 2019-06-03 |  | 2019-09-07 | [8 empty] | LM Winders
Project Name 47 | Project Number47 | Project Manager47 | Program Manager47 | Pre-Construction | Location47 | NI | Contact47 | TRUE | 840 | 2019-06-03 |  | 2019-09-07 | [5 empty] | 222042 | 222042 |  | LM Winders
Project Name 48 | Project Number48 | Project Manager48 | Program Manager48 | Pre-Construction | Location48 | SI | Contact48 | FALSE |  | 2019-10-01 |  | 2019-11-30 | [8 empty] | SI Elect | 2019-10-01 | 2019-11-30 | [9 empty] | 600 | SI Civil | 2019-10-01 | 2019-11-30 | [9 empty] | 900
Project Name 49 | Project Number49 | Project Manager49 | Program Manager49 | Pre-Construction | Location49 | SI | Contact49 | FALSE | 600 | 2019-07-22 |  | 2019-08-28 | [8 empty] | SI MASS (MECH)
Project Name 50 | Project Number50 | Project Manager50 | Program Manager50 | Pre-Construction | Location50 | SI | Contact50 | FALSE | 7200 | 2021-06-21 |  | 2022-09-21
Project Name 51 | Project Number51 | Project Manager51 | Program Manager51 | Completion | Location51 | SI | Contact51 | TRUE |  | 2018-04-02 | 2018-04-02 | 2018-08-31 | 2018-08-31 | 2018-06-18 | 2018-07-03 | 2018-10-31 | 2018-10-26 | 1669153 | 2337667 |  | SI Civil
Project Name 52 | Project Number52 | Project Manager52 | Program Manager52 | Completion | Location52 | SI | Contact52 | FALSE | 6000 |  | 2017-05-01 |  | 2019-03-29 |  | 2017-05-01 | 2019-04-26 | 2019-04-05 | 1427000 | 1454557 | 1411000 | SI Elect
Project Name 53 | Project Number53 | Project Manager53 | Program Manager53 | Construction | Location53 | SI | Contact53 | FALSE | 2700 | 2019-04-01 | 2019-04-01 | 2019-09-20 | 2019-09-20 | 2019-04-01 | 2019-04-01 | 2019-09-20 |  | 572000 | 572000 |  | SI Elect
Project Name 54 | Project Number54 | Project Manager54 | Program Manager54 | Construction | Location54 | SI | Contact54 | TRUE | 1800 | 2019-04-01 | 2019-04-23 | 2019-05-10 | 2019-06-21 | 2019-04-23 | 2019-04-23 | 2019-06-21 |  | 582000 | 582000 |  | SI Civil
Project Name 55 | Project Number55 | Project Manager55 | Program Manager55 | Completion | Location55 | SI | Contact55 | FALSE | 1050 | 2018-07-16 | 2018-10-22 | 2019-03-01 | 2019-03-01 | 2018-10-22 | 2018-10-22 | 2019-03-01 | 2019-03-01 | 80000 | 80000 |  | SI Elect
Project Name 56 | Project Number56 | Project Manager56 | Program Manager56 | Pre-Construction | Location56 | SI | Contact56 | FALSE | 900 | 2019-06-10 |  | 2019-07-26 | [8 empty] | SI Elect
Project Name 57 | Project Number57 | Project Manager57 | Program Manager57 | Pre-Construction | Location57 | SI | Contact57 | FALSE |  | 2019-05-13 | 2019-05-13 | 2019-10-25 | 2019-10-25 | 2019-05-13 |  | 2019-10-25 |  |  |  |  | SI Elect | 2019-05-13 | 2019-06-07 | 2019-05-13 | 2019-06-07 | 2019-05-13 | 2019-06-07 | [5 empty] | 450 | SI Elect | 2019-07-29 | 2019-10-25 | 2019-07-29 | 2019-10-25 | 2019-07-29 | 2019-10-25 | [5 empty] | 1350
Project Name 58 | Project Number58 | Project Manager58 | Program Manager58 | Construction | Location58 | SI | Contact58 | TRUE | 1200 | 2019-06-03 | 2019-06-17 | 2019-09-27 | 2019-11-01 | 2019-06-17 | 2019-04-17 | 2019-09-27 |  | 218000 | 218000 |  | SI Elect
Project Name 59 | Project Number59 | Project Manager59 | Program Manager59 | Pre-Construction | Location59 | SI | Contact59 | FALSE | 1500 | 2021-04-01 |  | 2021-09-30 | [8 empty] | SI Elect
Project Name 60 | Project Number60 | Project Manager60 | Program Manager60 | Pre-Construction | Location60 | SI | Contact60 | FALSE | 900 | 2019-08-19 |  | 2019-10-11 | [8 empty] | SI Elect | 2019-09-03 | 2019-10-11 | [9 empty] | 2250 | SI Civil | 2019-09-03 | 2019-10-11 | [9 empty] | 900
Project Name 61 | Project Number61 | Project Manager61 | Program Manager61 | Pre-Construction | Location61 | SI | Contact61 | FALSE | 150 | 2019-04-01 | 2019-04-01 | 2019-05-03 | 2019-05-03 | 2019-05-27 |  | 2019-07-12 |  | 40000 | 40000 |  | SI Elect
Project Name 62 | Project Number62 | Project Manager62 | Program Manager62 | Pre-Construction | Location62 | SI | Contact62 | FALSE | 1500 | 2019-07-15 |  | 2019-11-15 | [8 empty] | SI Elect
Project Name 63 | Project Number63 | Project Manager63 | Program Manager63 | Pre-Construction | Location63 | SI | Contact63 | TRUE |  | 2019-05-06 | 2019-05-06 | 2019-11-22 | 2019-11-22 | 2019-05-06 |  | 2019-11-22 |  | 748000 | 748000 |  | SI Elect | 2019-05-27 | 2019-11-22 | 2019-05-27 | 2019-11-22 | 2019-05-27 | 2019-11-22 |  |  | 130000 | 130000 |  | 1270 | SI Civil | 2019-05-06 | 2019-09-27 | 2019-05-06 | 2019-09-27 | 2019-05-06 | 2019-09-27 |  |  | 422000 | 422000 |  | 2250
Project Name 64 | Project Number64 | Project Manager64 | Program Manager64 | Pre-Construction | Location64 | SI | Contact64 | TRUE |  | 2019-04-01 | 2019-04-15 | 2019-08-31 | 2019-08-30 | 2019-05-13 |  | 2019-09-20 |  | 610000 | 610000 |  |  | 2019-04-01 | 2019-08-30 | 2019-04-15 | 2019-08-30 | 2019-05-13 | 2019-09-20 |  |  | 410000 | 410000 |  | 2413 |  | 2019-04-01 | 2019-08-30 | 2019-04-15 | 2019-08-30 | 2019-05-13 | 2019-09-20 |  |  | 200000 | 200000 |  | 1520
Project Name 65 | Project Number65 | Project Manager65 | Program Manager65 | Construction | Location65 | LM | Contact65 | FALSE |  |  | 2018-01-08 |  | 2018-02-09 |  | 2018-01-15 | 2019-07-27 |  | 240000 | 284604 |  | LM Civil |  |  | 2018-01-08 | 2018-02-02 | 2018-01-08 |  | 2018-01-15 | 2018-02-15 | 104887 |  |  | 510 | LM Line |  | 2019-06-03 | 2018-02-02 |  | 2018-02-02 |  |  | 2018-02-15 | 65142 |  |  | 645 | LM Field Mech |  |  | 2018-01-08 | 2018-01-15 | 2018-01-08 |  | 2018-01-15 | 2018-01-21 | 69971 |  |  | 37.5
Project Name 66 | Project Number66 | Project Manager66 | Program Manager66 | Construction | Location66 | LM | Contact66 | TRUE |  |  | 2018-06-18 |  | 2018-10-31 |  | 2018-05-21 | 2019-05-03 |  | 491850 | 769583 |  | LM Line |  |  | 2018-06-18 | 2018-10-31 | 2018-06-18 | 2019-04-05 | 2018-05-21 |  | 265881 | 121171 |  | 2330 | LM Civil |  |  | 2018-06-18 | 2018-08-04 | 2018-06-18 |  | 2018-09-28 | 2018-05-28 | 225969 | 648412 |  | 1054.5
Project Name 67 | Project Number67 | Project Manager67 | Program Manager67 | Construction | Location67 | LM | Contact67 | TRUE | 5820 |  | 2018-09-01 |  | 2019-09-30 |  | 2018-08-13 | 2019-07-31 |  | 1064500 | 859964 |  | LM Line
Project Name 68 | Project Number68 | Project Manager68 | Program Manager68 | Construction | Location68 | LM | Contact68 | FALSE |  | 2019-04-03 | 2019-04-03 | 2019-08-30 | 2019-04-26 | 2019-04-03 | 2019-04-03 | 2019-04-26 |  |  |  |  | LM Civil | 2019-04-03 | 2019-04-26 | 2019-04-03 | 2019-04-26 | 2019-04-03 | 2019-04-26 | 2019-04-03 |  | 88567 | 88567 |  | 810 | LM Field Mech | 2019-05-06 | 2019-06-28 | [6 empty] | 35436 | 35436 |  | 500 | LM Line | 2019-07-01 | 2019-08-30 | [9 empty] | 1050
Project Name 69 | Project Number69 | Project Manager69 | Program Manager69 | Completion | Location69 | LM | Contact69 | FALSE |  |  | 2018-04-01 |  | 2018-11-16 | 2018-04-01 | 2018-09-17 | 2019-04-26 | 2019-04-26 | 1029375 | 1384383 |  | LM Line |  |  | 2018-04-01 | 2018-08-31 | 2018-09-17 | 2019-03-29 | 2018-09-17 | 2019-04-26 | 1029375 | 1173521 |  | 10035 | LM Civil |  |  | 2018-10-15 | 2018-11-16 | 2018-10-15 | 2019-03-15 | 2019-04-12 | 2018-10-24 | 0 | 210862 |  | 1263.5
Project Name 70 | Project Number70 | Project Manager70 | Program Manager70 | Construction | Location70 | NI | Contact70 | TRUE | 2821 | 2019-04-01 | 2019-04-01 | 2019-07-20 | 2019-07-20 | 2019-04-01 | 2019-04-01 | 2019-07-20 |  | 335536 | 335536
Project Name 71 | Project Number71 | Project Manager71 | Program Manager71 | Pre-Construction | Location71 | LM | Contact71 | FALSE | 3500 | 2019-08-19 |  | 2020-01-31 | [8 empty] | LM Elect2
Project Name 72 | Project Number72 | Project Manager72 | Program Manager72 | Construction | Location72 | SI | Contact72 | FALSE | 300 | 2018-09-04 | 2018-09-04 |  | 2018-12-01 | 2018-09-04 | 2018-09-04 | 2019-05-17 |  | 60000 | 60000 |  | SI Elect
Project Name 73 | Project Number73 | Project Manager73 | Program Manager73 | Pre-Construction | Location73 | LM | Contact73 | TRUE | 600 |  | 2019-07-29 |  | 2019-09-15 | 2019-07-29 |  | 2019-09-15 |  | 444631 | 444631 |  | LM Civil
Project Name 74 | Project Number74 | Project Manager74 | Program Manager74 | Pre-Construction | Location74 | LM | Contact74 | FALSE | 1200 | 2019-08-15 |  | 2019-10-16 | [8 empty] | LM Elect1 | 2019-08-15 | 2019-10-16 | [9 empty] | 1200 | LM Civil | 2019-08-15 | 2019-10-16 | [9 empty] | 600 | LM Field Mech | 2019-08-15 | 2019-10-16 | [9 empty] | 600
Project Name 75 | Project Number75 | Project Manager75 | Program Manager75 | Pre-Construction | Location75 | LM NI | Contact75 | FALSE | 2600 | 2019-04-01 |  | 2020-03-31
Project Name 76 | Project Number76 | Project Manager76 | Program Manager76 | Completion | Location76 | LM | Contact76 | TRUE | 350 | 2019-01-14 | 2018-05-01 | 2019-02-28 | 2019-03-31 | 2018-05-01 | 2018-05-01 | 2019-06-28 |  | 440762 | 688196 |  | LM Elect2
Project Name 77 | Project Number77 | Project Manager77 | Program Manager77 | Pre-Construction | Location77 | LM | Contact77 | FALSE | 150 | 2019-04-01 |  | 2019-04-12 | [8 empty] | LM Elect2
Project Name 78 | Project Number78 | Project Manager78 | Program Manager78 | Pre-Construction | Location78 | LM | Contact78 | FALSE |  | 2019-05-02 | 2019-05-02 | 2019-07-02 | 2019-07-02 | 2019-05-02 |  | 2019-07-02 |  |  |  |  | LM Elect1 | 2019-05-02 | 2019-07-02 | 2019-05-02 | 2019-07-02 | 2019-05-02 |  |  |  | 161437 | 161437 |  | 1050 | LM Civil | 2019-05-02 | 2019-07-02 | 2019-05-02 | 2019-07-02 | 2019-05-02 |  |  |  | 70880 | 70880 |  | 630
Project Name 79 | Project Number79 | Project Manager79 | Program Manager79 | Pre-Construction | Location79 | LM | Contact79 | FALSE |  | 2019-05-13 |  | 2019-11-30 | [8 empty] | LM Elect1 | 2019-05-13 | 2019-11-30 | [9 empty] | 2800 | LM Line | 2019-05-13 | 2019-11-30 | [9 empty] | 1000 | LM Civil | 2019-05-13 | 2019-06-30 | [9 empty] | 400
Project Name 80 | Project Number80 | Project Manager80 | Program Manager80 | Pre-Construction | Location80 | LM | Contact80 | FALSE | 200 | 2019-03-04 | 2019-03-04 | 2019-03-29 | 2019-03-29 | 2019-04-15 |  | 2019-05-03 |  | 41355 | 41355
Project Name 81 | Project Number81 | Project Manager81 | Program Manager81 | Construction | Location81 | LM | Contact81 | FALSE | 150 | 2019-03-25 | 2019-03-25 | 2019-03-31 | 2019-03-31 | 2019-03-25 | 2019-03-25 | 2019-03-31 |  | 28732 | 28732
Project Name 82 | Project Number82 | Project Manager82 | Program Manager82 | Pre-Construction | Location82 | LM | Contact82 | FALSE | 250 | 2019-05-08 |  | 2019-05-24 | [5 empty] | 45120 | 45120
Project Name 83 | Project Number83 | Project Manager83 | Program Manager83 | Pre-Construction | Location83 | LM | Contact83 | FALSE | 1350 | 2019-09-02 |  | 2019-12-16 | [8 empty] | LM Elect2
Project Name 84 | Project Number84 | Project Manager84 | Program Manager84 | Construction | Location84 | LM | Contact84 | TRUE | 6000 | 2019-02-01 | 2019-02-01 | 2020-06-01 | 2020-06-01 | 2019-02-01 | 2019-02-01 | 2020-06-01 |  | 1211684 | 1002168 |  | LM Elect2
Project Name 85 | Project Number85 | Project Manager85 | Program Manager85 | Pre-Construction | Location85 | LM | Contact85 | FALSE | 450 | 2019-07-01 |  | 2019-08-15 | [5 empty] | 63595 | 63595 |  | LM Elect2
Project Name 86 | Project Number86 | Project Manager86 | Program Manager86 | Pre-Construction | Location86 | LM | Contact86 | FALSE | 2250 | 2019-11-01 |  | 2020-03-31 | [8 empty] | LM Elect2
Project Name 87 | Project Number87 | Project Manager87 | Program Manager87 | Pre-Construction | Location87 | LM | Contact87 | FALSE | 2100 | 2019-05-15 |  | 2019-09-30 | [8 empty] | LM Elect1 | 2019-05-15 | 2019-09-30 | [9 empty] | 2100 | LM Civil | 2019-05-15 | 2019-09-30 | [9 empty] | 1000
Project Name 88 | Project Number88 | Project Manager88 | Program Manager88 | Construction | Location88 | LM | Contact88 | FALSE |  | 2018-06-25 | 2018-06-25 | 2019-08-16 | 2019-04-24 | 2018-06-25 | 2018-06-25 | 2019-08-16 |  | 1373631 | 1272189 |  | LM Civil |  | 2018-06-26 | 2018-06-25 | 2018-06-26 | 2018-06-25 |  | 2018-06-25 | 2018-06-26 | 421783 | 409611 |  | 2100 | LM Elect1 | 2018-06-25 | 2019-04-24 | 2018-06-25 | 2019-04-24 | 2018-06-25 | 2019-08-16 |  | 2018-06-25 | 720133 | 680134 |  | 7200
Project Name 89 | Project Number89 | Project Manager89 | Program Manager89 | Completion | Location89 | VI | Contact89 | TRUE |  |  | 2018-06-25 |  | 2019-01-01 | 2018-07-24 | 2018-07-24 | 2019-03-31 | 2019-03-27 | 585432 | 572286 |  | VI Line
Project Name 90 | Project Number90 | Project Manager90 | Program Manager90 | Construction | Location90 | NI | Contact90 | TRUE | 1995 | 2019-03-18 | 2019-03-18 | 2019-06-01 | 2019-06-01 | 2019-03-18 | 2019-03-18 | 2019-06-01 |  | 396742 | 396742 |  | LM Winders
Project Name 91 | Project Number91 | Project Manager91 | Program Manager91 | Construction | Location91 | LM | Contact91 | TRUE | 697.5 | 2019-01-21 | 2019-01-28 | 2019-03-21 | 2019-03-21 | 2019-01-28 | 2019-01-28 | 2019-05-31 |  | 105535 | 105535 |  | LM Winders
Project Name 92 | Project Number92 | Project Manager92 | Program Manager92 | Construction | Location92 | VI | Contact92 | TRUE | 405 | 2019-05-06 | 2019-05-06 | 2019-05-14 | 2019-05-14 | 2019-04-26 | 2019-04-26 | 2019-05-14 |  | 48255 | 48255 |  | LM Winders
Project Name 93 | Project Number93 | Project Manager93 | Program Manager93 | Construction | Location93 | VI | Contact93 | TRUE | 795 | 2019-03-11 | 2019-03-18 | 2019-04-06 | 2019-04-06 | 2019-03-11 | 2019-03-11 | 2019-05-07 |  | 152622 | 152622 |  | LM Winders
Project Name 94 | Project Number94 | Project Manager94 | Program Manager94 | Construction | Location94 | NI | Contact94 | TRUE | 892 | 2019-04-08 | 2019-04-08 | 2019-05-10 | 2019-05-10 | 2019-04-08 | 2019-04-08 | 2019-05-10 |  | 199845 | 199845 |  | LM Winders
Project Name 95 | Project Number95 | Project Manager95 | Program Manager95 | Pre-Construction | Location95 | LM | Contact95 | TRUE | 997 | 2018-07-01 |  | 2018-08-15 | [8 empty] | LM Winders
Project Name 96 | Project Number96 | Project Manager96 | Program Manager96 | Pre-Construction | Location96 | LM | Contact96 | TRUE | 997 | 2019-01-07 |  | 2019-02-23 | [8 empty] | LM Winders
Project Name 97 | Project Number97 | Project Manager97 | Program Manager97 | Pre-Construction | Location97 | VI | Contact97 | TRUE | 937 | 2018-10-15 |  | 2018-11-09 | [8 empty] | LM Winders
Project Name 98 | Project Number98 | Project Manager98 | Program Manager98 | Pre-Construction | Location98 | LM | Contact98 | TRUE | 1350 | 2019-07-15 |  | 2019-09-27 | [5 empty] | 222108 | 222108 |  | LM Winders
Project Name 99 | Project Number99 | Project Manager99 | Program Manager99 | Pre-Construction | Location99 | LM | Contact99 | TRUE | 1230 | [11 empty] | LM Winders
Project Name 100 | Project Number100 | Project Manager100 | Program Manager100 | Pre-Construction | Location100 | SI | Contact100 | TRUE | 1350 | 2019-09-09 |  | 2019-11-17 | [5 empty] | 326400 |  |  | LM Winders
Project Name 101 | Project Number101 | Project Manager101 | Program Manager101 | Pre-Construction | Location101 | VI | Contact101 | FALSE | 675 | 2019-07-10 | [7 empty] | 92590 | 92590 |  | LM Winders
Project Name 102 | Project Number102 | Project Manager102 | Program Manager102 | Pre-Construction | Location102 | LM | Contact102 | TRUE | 480 | 2020-04-01 |  | 2020-04-24 | [5 empty] | 80000 |  |  | LM Winders
Project Name 103 | Project Number103 | Project Manager103 | Program Manager103 | Construction | Location103 | VI | Contact103 | TRUE | 712 | 2019-04-23 | 2019-04-23 | 2019-05-20 | 2019-04-20 | 2019-05-20 |  | 2019-06-10 |  | 94588 | 94588 |  | LM Winders
Project Name 104 | Project Number104 | Project Manager104 | Program Manager104 | Construction | Location104 | LM | Contact104 | TRUE | 2480 | 2019-02-25 | 2019-02-25 | 2019-04-05 | 2019-04-05 | 2019-02-25 | 2019-02-25 | 2020-01-01 |  | 340000 | 394545 |  | LM Civil
Project Name 105 | Project Number105 | Project Manager105 | Program Manager105 | Pre-Construction | Location105 | LM | Contact105 | FALSE | 560 | 2019-05-01 |  | 2019-07-01 | [8 empty] | LM Line
Project Name 106 | Project Number106 | Project Manager106 | Program Manager106 | Pre-Construction | Location106 | LM | Contact106 | FALSE | 1000 | 2019-04-22 |  | 2019-06-28 | [8 empty] | LM Line
Project Name 107 | Project Number107 | Project Manager107 | Program Manager107 | Pre-Construction | Location107 | LM | Contact107 | FALSE | 4000 | 2019-04-15 |  | 2019-08-30 | [8 empty] | LM Line
Project Name 108 | Project Number108 | Project Manager108 | Program Manager108 | Completion | Location108 | SI | Contact108 | TRUE |  |  | 2018-10-09 | 2019-05-31 | 2019-05-31 |  | 2018-10-09 |  | 2019-04-02 | 70859 | 85856 |  | LM Winders
Project Name 109 | Project Number109 | Project Manager109 | Program Manager109 | Pre-Construction | Location109 | LM | Contact109 | FALSE | 300 | 2019-09-02 |  | 2019-10-31 | [8 empty] | LM Elect2 | 2019-09-02 | 2019-10-31 | [9 empty] | 300 | LM Civil | 2019-10-31 | 2019-10-31 | [9 empty] | 300
Project Name 110 | Project Number110 | Project Manager110 | Program Manager110 | Construction | Location110 | NI | Contact110 | TRUE | 9897 | 2018-04-12 | 2018-04-12 | 2018-12-17 | 2018-12-17 |  | 2018-04-12 | 2019-07-31 |  | 1038385 | 934867 |  | NI Elect
Project Name 111 | Project Number111 | Project Manager111 | Program Manager111 | Pre-Construction | Location111 | NI | Contact111 | FALSE |  | 2021-04-01 |  | 2021-11-30 | [8 empty] | NI Civil | [11 empty] | 5200 | NI Elect | [11 empty] | 8600
Project Name 112 | Project Number112 | Project Manager112 | Program Manager112 | Construction | Location112 | NI | Contact112 | TRUE | 3400 | 2019-04-01 | 2019-04-08 | 2019-07-01 | 2019-07-28 | 2019-04-08 | 2019-04-08 | 2019-07-28 |  | 424197 |  |  | NI Elect
Project Name 113 | Project Number113 | Project Manager113 | Program Manager113 | Construction | Location113 | VI | Contact113 | TRUE |  |  | 2019-04-01 |  | 2019-08-31 | 2019-04-01 | 2019-04-23 | 2019-08-31 |  | 791633 | 791633 |  | VI Elect |  |  | 2019-04-01 | 2019-08-31 | 2019-04-01 | 2019-08-31 | 2019-04-23 |  | 392823 | 392823 |  | 4958 | VI Civil |  |  | 2019-04-01 | 2019-08-31 | 2019-04-01 | 2019-08-31 |  | 2019-04-23 | 327082 | 327082 |  | 1758
Project Name 114 | Project Number114 | Project Manager114 | Program Manager114 | Construction | Location114 | VI | Contact114 | FALSE | 22468 |  | 2018-05-05 |  | 2019-11-30 |  | 2018-04-16 | 2020-03-30 |  | 2012000 | 2027697 |  | VI Elect
Project Name 115 | Project Number115 | Project Manager115 | Program Manager115 | Pre-Construction | Location115 | SI | Contact115 | TRUE | 3000 | 2019-04-15 | 2019-04-01 | 2019-08-31 | 2019-08-31 | 2019-09-09 |  | 2019-12-13 |  | 413000 | 413000 |  | SI Line
Project Name 116 | Project Number116 | Project Manager116 | Program Manager116 | Pre-Construction | Location116 | SI | Contact116 | FALSE | 870 | 2019-09-03 |  | 2019-10-11 | [8 empty] | SI Civil
Project Name 117 | Project Number117 | Project Manager117 | Program Manager117 | Pre-Construction | Location117 | SI | Contact117 | FALSE | 180 | 2019-10-15 |  | 2019-10-25 | [8 empty] | SI Civil
Project Name 118 | Project Number118 | Project Manager118 | Program Manager118 | Pre-Construction | Location118 | NI | Contact118 | FALSE | 300 | 2019-07-01 |  | 2019-08-09 | [8 empty] | LM Civil
Project Name 119 | Project Number119 | Project Manager119 | Program Manager119 | Pre-Construction | Location119 | LM | Contact119 | TRUE | 1350 |  | 2018-09-04 |  | 2019-03-31 | 2019-09-15 |  | 2019-12-31 |  | 128000 | 128000 |  | LM Civil
Project Name 120 | Project Number120 | Project Manager120 | Program Manager120 | Pre-Construction | Location120 | LM | Contact120 | TRUE |  | 2019-09-02 |  | 2019-10-31 | [5 empty] | 0 | 0 |  | LM Civil | 2019-09-02 | 2019-10-31 | [9 empty] | 1125 | LM Elect1 | 2019-09-02 | 2019-10-31 | [9 empty] | 300
Project Name 121 | Project Number121 | Project Manager121 | Program Manager121 | Construction | Location121 | LM | Contact121 | TRUE | 600 | 2019-04-03 | 2019-04-03 | 2019-04-26 | 2019-04-26 |  | 2019-04-03 | 2019-04-26 |  | 97556 | 97556 |  | LM Civil
Project Name 122 | Project Number122 | Project Manager122 | Program Manager122 | Pre-Construction | Location122 | LM | Contact122 | TRUE | 1200 | 2019-09-01 |  | 2019-10-31 | [8 empty] | LM Civil
Project Name 123 | Project Number123 | Project Manager123 | Program Manager123 | Construction | Location123 | LM | Contact123 | FALSE | 150 |  | 2018-02-19 |  | 2018-03-30 | 2018-02-19 | 2018-02-19 | 2019-09-30 |  | 176410 | 146501 |  | LM Civil
Project Name 124 | Project Number124 | Project Manager124 | Program Manager124 | Pre-Construction | Location124 | SI | Contact124 | FALSE | 970 | 2019-09-03 |  | 2019-10-11 | [8 empty] | SI Civil
Project Name 125 | Project Number125 | Project Manager125 | Program Manager125 | Construction | Location125 | LM | Contact125 | TRUE |  |  | 2017-05-30 |  | 2018-11-08 |  | 2017-05-30 | 2019-09-30 |  | 6987514 | 5260110 |  | LM Elect1 |  |  | 2017-05-30 | 2018-11-08 | 2017-05-30 |  | 2017-05-30 | 2019-04-15 | 3046929 | 2113878 |  | 25720 | LM Civil |  |  | 2017-05-30 | 2018-10-22 | 2017-05-30 |  | 2019-04-15 | 2017-05-30 | 3323571 | 2771157 |  | 12726 | LM Winders |  |  | 2018-03-23 | 2018-05-09 | 2018-03-23 |  | 2018-03-12 | 2018-04-19 | 138531 | 43782 |  | 1400 | LM Line |  |  | 2017-08-02 | 2018-03-12 | 2017-08-02 |  | 2017-08-02 | 2018-03-19 | 362145 | 121756 |  | 4028
Project Name 126 | Project Number126 | Project Manager126 | Program Manager126 | Completion | Location126 | SI | Contact126 | TRUE | 500 | 2019-02-04 | 2019-03-05 | 2019-04-26 | 2019-04-12 | 2019-03-05 | 2019-03-05 | 2019-04-12 | 2019-03-15 | 92629 | 70000 | 70000 | SI Elect
Project Name 127 | Project Number127 | Project Manager127 | Program Manager127 | Pre-Construction | Location127 | SI | Contact127 | FALSE |  | 2019-03-04 | 2019-05-06 | 2019-08-30 | 2019-08-30 | 2019-05-06 |  | 2019-08-30 |  | 53581 | 53581 |  | SI Civil | 2019-05-06 | 2019-08-30 | 2019-05-06 | 2019-05-20 | 2019-05-06 |  |  |  | 32402 | 32402 |  | 120 | SI Elect | 2019-05-20 | 2019-08-30 | 2019-05-20 | 2019-06-14 | 2019-05-20 |  |  |  | 12041 | 12041 |  | 50
Project Name 128 | Project Number128 | Project Manager128 | Program Manager128 | Pre-Construction | Location128 | SI | Contact128 | TRUE | 1600 | 2019-04-22 | 2019-04-22 | 2019-07-31 | 2019-07-31 | 2019-04-22 |  | 2019-07-31 |  |  |  |  | SI Line
Project Name 129 | Project Number129 | Project Manager129 | Program Manager129 | Pre-Construction | Location129 | SI | Contact129 | FALSE |  | 2019-03-04 | 2019-05-20 | 2019-08-30 | 2019-08-30 | 2019-05-20 |  | 2019-08-30 |  | 43025 | 43025 |  | SI Civil | 2019-03-04 | 2019-08-30 | 2019-05-20 | 2019-06-03 | 2019-05-20 |  |  |  | 21845 | 21845 |  | 120 | SI Elect | 2019-03-04 | 2019-08-30 | 2019-06-03 | 2019-07-03 | 2019-06-03 |  |  |  | 12401 | 12401 |  | 50
Project Name 130 | Project Number130 | Project Manager130 | Program Manager130 | Pre-Construction | Location130 | SI | Contact130 | TRUE | 12000 |  | 2017-03-01 |  | 2017-11-01 | 2019-07-29 |  | 2020-03-31 |  | 1612997 |  |  | SI Line
Project Name 131 | Project Number131 | Project Manager131 | Program Manager131 | Construction | Location131 | SI | Contact131 | TRUE | 420 |  | 2018-11-21 |  | 2019-03-31 | 2018-11-26 | 2018-11-26 | 2019-11-12 |  | 64000 | 64000 |  | SI MASS (SS)
Project Name 132 | Project Number132 | Project Manager132 | Program Manager132 | Construction | Location132 | SI | Contact132 | TRUE | 2540 | 2019-03-20 | 2019-03-20 | 2019-05-10 | 2019-05-10 | 2019-03-20 | 2019-03-20 | 2019-05-10 |  | 528000 | 577485 |  | SI MASS (SS)
Project Name 133 | Project Number133 | Project Manager133 | Program Manager133 | Completion | Location133 | SI | Contact133 | TRUE | 990 | 2019-02-04 | 2019-02-04 | 2019-03-29 | 2019-03-29 | 2019-02-04 | 2019-02-04 | 2019-04-12 | 2019-04-12 | 152426 | 167000 | 167000 | SI Civil
Project Name 134 | Project Number134 | Project Manager134 | Program Manager134 | Construction | Location134 | SI | Contact134 | FALSE |  | 2019-03-04 | 2019-04-23 | 2019-08-30 | 2019-05-31 | 2019-04-23 | 2019-04-23 | 2019-05-31 |  | 59481 | 59481 |  | SI Civil | 2019-04-23 | 2019-05-03 | 2019-04-23 | 2019-05-01 | 2019-04-23 | 2019-05-01 | 2019-04-23 |  | 38302 | 38302 |  | 150 | SI Elect | 2019-05-01 | 2019-05-31 | 2019-05-06 | 2019-05-31 | 2019-05-06 |  |  |  | 12401 | 12401 |  | 80
Project Name 135 | Project Number135 | Project Manager135 | Program Manager135 | Pre-Construction | Location135 | VI | Contact135 | FALSE | 2378 | 2019-05-13 | 2019-05-13 | 2019-06-14 | 2019-06-14 | 2019-05-13 |  | 2019-06-14 |  | 317324 | 317324 |  | VI Civil
Project Name 136 | Project Number136 | Project Manager136 | Program Manager136 | Construction | Location136 | SI | Contact136 | TRUE |  | 2019-03-18 | 2019-03-18 | 2019-05-17 | 2019-05-17 | 2019-03-18 | 2019-03-18 | 2019-05-01 |  | 227000 | 227000 |  | SI MASS (MECH) | 2019-03-18 | 2019-05-17 | 2019-03-18 | 2019-05-17 | 2019-03-18 |  | 2019-03-18 |  | 207000 | 207000 |  | 1140 | SI Elect | 2019-03-18 | 2019-04-26 | 2019-03-18 | 2019-04-26 | 2019-03-18 | 2019-04-26 |  | 2019-03-18 | 20000 | 20000 |  | 200
Project Name 137 | Project Number137 | Project Manager137 | Program Manager137 | Construction | Location137 | SI | Contact137 | TRUE | 3220 |  | 2018-09-17 |  | 2019-05-16 |  | 2018-09-17 | 2019-05-16 |  | 422576 | 494202 |  | SI Elect
Project Name 138 | Project Number138 | Project Manager138 | Program Manager138 | Construction | Location138 | SI | Contact138 | TRUE | 1500 | 2019-02-04 | 2019-02-04 | 2019-05-17 | 2019-05-17 | 2019-02-04 | 2019-02-04 | 2019-05-17 |  | 502191 | 497055 |  | SI MASS (MECH) | 2019-02-04 | 2019-05-17 | 2019-02-04 | 2019-05-17 | 2019-02-04 | 2019-05-17 | 2019-02-04 |  | 294475 | 309073 |  | 1500 | SI Elect | 2019-02-04 | 2019-05-17 | 2019-02-04 | 2019-05-17 | 2019-02-04 | 2019-05-17 |  | 2019-02-04 | 207715 | 187981 |  | 1600
Project Name 139 | Project Number139 | Project Manager139 | Program Manager139 | Pre-Construction | Location139 | VI | Contact139 | TRUE |  | 2019-04-01 |  | 2019-05-13 | [5 empty] | 228247 | 228247 |  | VI Civil | 2019-04-01 | 2019-05-13 | 2019-04-01 |  | 2019-05-01 |  |  |  | 168464 | 168464 |  | 855 | VI Elect | 2019-04-01 | 2019-05-13 | 2019-04-01 |  | 2019-05-01 |  |  |  | 59783 | 59783 |  | 513
Project Name 140 | Project Number140 | Project Manager140 | Program Manager140 | Pre-Construction | Location140 | LM | Contact140 | FALSE | 300 |  | 2018-10-15 | 2018-11-15 | 2018-11-15 | 2019-10-15 |  | 2019-11-01 |  | 147314 | 147314 |  | LM Civil
Project Name 141 | Project Number141 | Project Manager141 | Program Manager141 | Pre-Construction | Location141 | VI | Contact141 | FALSE | 300 | 2019-06-03 | 2019-06-03 | 2019-06-14 | 2019-06-14 | 2019-06-03 |  | 2019-06-14 |  | 62000 | 62000 |  | VI Civil
Project Name 142 | Project Number142 | Project Manager142 | Program Manager142 | Pre-Construction | Location142 | VI | Contact142 | FALSE | 5010 | 2019-07-02 | 2019-07-02 | 2019-10-25 | 2019-10-25 | 2019-07-02 |  | 2019-10-25 |  |  |  |  | VI Civil
Project Name 143 | Project Number143 | Project Manager143 | Program Manager143 | Pre-Construction | Location143 | VI | Contact143 | FALSE | 1200 | 2019-07-02 | 2019-07-02 | 2019-10-01 | 2019-10-01 | 2019-07-02 |  | 2019-10-01 |  |  |  |  | VI Civil
Project Name 144 | Project Number144 | Project Manager144 | Program Manager144 | Pre-Construction | Location144 | SI | Contact144 | TRUE |  |  | 2018-11-19 |  | 2018-12-05 |  | 2018-11-19 | 2019-01-18 |  | 232000 | 232000 |  | SI MASS (MECH) | 2018-11-19 | 2019-01-18 | [6 empty] | 170000 | 170000 |  | 551 | SI Elect | 2018-11-19 | 2019-01-18 | [6 empty] | 62000 | 62000 |  | 475
Project Name 145 | Project Number145 | Project Manager145 | Program Manager145 | Pre-Construction | Location145 | SI | Contact145 | FALSE | 1610 | 2019-11-13 |  | 2019-12-13 | [8 empty] | SI MASS (SS)
Project Name 146 | Project Number146 | Project Manager146 | Program Manager146 | Pre-Construction | Location146 | SI | Contact146 | FALSE | 1340 | 2019-07-08 |  | 2019-07-31 | [8 empty] | SI MASS (SS)
Project Name 147 | Project Number147 | Project Manager147 | Program Manager147 | Pre-Construction | Location147 | SI | Contact147 | FALSE | 600 | 2020-03-02 |  | 2020-03-13 | [8 empty] | SI MASS (SS)
Project Name 148 | Project Number148 | Project Manager148 | Program Manager148 | Pre-Construction | Location148 | LM | Contact148 | FALSE | 380 | 2019-08-26 |  | 2019-09-06 | [8 empty] | SI MASS (SS)
Project Name 149 | Project Number149 | Project Manager149 | Program Manager149 | Pre-Construction | Location149 | SI | Contact149 | FALSE | 1740 | 2019-07-22 |  | 2019-08-28 | [8 empty] | SI MASS (MECH)
Project Name 150 | Project Number150 | Project Manager150 | Program Manager150 | Pre-Construction | Location150 | SI | Contact150 | FALSE | 1400 | 2020-07-06 |  | 2020-07-31 | [8 empty] | SI MASS (SS)
Project Name 151 | Project Number151 | Project Manager151 | Program Manager151 | Pre-Construction | Location151 | SI | Contact151 | FALSE | 2100 | 2019-05-13 |  | 2019-06-21 | [5 empty] | 0 | 0 |  | SI MASS (SS)
Project Name 152 | Project Number152 | Project Manager152 | Program Manager152 | Pre-Construction | Location152 | SI | Contact152 | FALSE | 630 | 2019-06-24 |  | 2019-07-05 | [5 empty] | 0 | 0 |  | SI MASS (SS)
Project Name 153 | Project Number153 | Project Manager153 | Program Manager153 | Pre-Construction | Location153 | SI | Contact153 | FALSE | 840 | 2019-07-02 |  | 2019-07-19 | [5 empty] | 0 | 0 |  | SI MASS (MECH)
Project Name 154 | Project Number154 | Project Manager154 | Program Manager154 | Pre-Construction | Location154 | LM | Contact154 | FALSE | 720 | 2019-08-12 |  | 2019-08-28 | [8 empty] | SI MASS (SS)
Project Name 155 | Project Number155 | Project Manager155 | Program Manager155 | Pre-Construction | Location155 | SI | Contact155 | FALSE | 1400 | 2019-09-16 |  | 2019-10-11 | [8 empty] | SI MASS (SS)
Project Name 156 | Project Number156 | Project Manager156 | Program Manager156 | Pre-Construction | Location156 | SI | Contact156 | FALSE | 980 | 2019-10-15 |  | 2019-11-01 | [5 empty] | 0 | 0 |  | SI MASS (SS)
Project Name 157 | Project Number157 | Project Manager157 | Program Manager157 | Pre-Construction | Location157 | SI | Contact157 | FALSE |  | 2020-01-20 |  | 2020-12-10 | [8 empty] | SI Elect | 2020-01-20 | 2020-12-10 | [9 empty] | 8250 | SI MASS (MECH) | 2020-05-11 | 2020-12-10 | [9 empty] | 5250
Project Name 158 | Project Number158 | Project Manager158 | Program Manager158 | Construction | Location158 | NI | Contact158 | FALSE | 5116 | 2019-02-20 | 2019-03-05 | 2019-06-26 | 2019-07-18 | 2019-03-05 | 2019-03-01 | 2019-07-18 |  | 517162 | 517162 |  | NI Elect
Project Name 159 | Project Number159 | Project Manager159 | Program Manager159 | Construction | Location159 | LM | Contact159 | TRUE |  | 2019-03-25 | 2019-03-25 | 2020-10-25 | 2020-10-25 | 2019-03-25 | 2019-03-25 | 2020-10-25 |  | 3500000 | 3500000 |  | LM Field Mech
Project Name 160 | Project Number160 | Project Manager160 | Program Manager160 | Completion | Location160 | LM | Contact160 | TRUE |  | 2019-01-02 | 2019-01-14 | 2019-03-21 | 2019-03-28 | 2019-01-14 | 2019-01-14 | 2019-03-28 | 2019-03-21 | 60000 | 60000 |  | LM Field Mech
Project Name 161 | Project Number161 | Project Manager161 | Program Manager161 | Construction | Location161 |  | Contact161 | FALSE | [6 empty] | 2019-04-18
Project Name 162 | Project Number162 | Project Manager162 | Program Manager162 | Pre-Construction | Location162 | NI | Contact162 | TRUE | 4200 | 2019-07-29 |  | 2020-05-29 | [8 empty] | NI Civil | 2019-07-29 | 2020-01-31 | [9 empty] | 4650 | NI Elect | 2019-08-26 | 2020-05-29 | [9 empty] | 6750
Project Name 163 | Project Number163 | Project Manager163 | Program Manager163 | Pre-Construction | Location163 | NI | Contact163 | TRUE |  | 2019-09-02 |  | 2021-03-31 | [8 empty] | NI Civil | 2019-09-02 | 2021-03-31 | [9 empty] | 25000 | NI Elect | 2019-09-02 | 2021-03-31 | [9 empty] | 30000
Project Name 164 | Project Number164 | Project Manager164 | Program Manager164 | Pre-Construction | Location164 | VI | Contact164 | FALSE | 2000 | 2019-09-01 |  | 2019-12-31
Project Name 165 | Project Number165 | Project Manager165 | Program Manager165 | Cancelled | Location165 | LM | Contact165 | TRUE |  | 2020-03-01 |  | 2020-12-01 | [8 empty] | LM Civil | 2020-03-01 | 2020-12-01 | [10 empty] | LM Elect1 | 2020-03-01 | 2020-12-01
Project Name 166 | Project Number166 | Project Manager166 | Program Manager166 | Pre-Construction | Location166 | SI | Contact166 | FALSE |  | 2019-05-01 |  | 2019-09-30 | [8 empty] | SI Civil | 2019-05-01 | 2019-09-13 | [9 empty] | 200 | SI Elect | 2019-05-01 | 2019-09-30 | [9 empty] | 200
Project Name 167 | Project Number167 | Project Manager167 | Program Manager167 | Pre-Construction | Location167 | SI | Contact167 | FALSE |  | 2019-05-01 | [10 empty] | SI Civil | 2019-05-01 | 2019-09-13 | [9 empty] | 200 | SI Elect | 2019-05-01 | 2019-09-30 | [9 empty] | 200
Project Name 168 | Project Number168 | Project Manager168 | Program Manager168 | Pre-Construction | Location168 | SI | Contact168 | FALSE |  | 2019-05-01 |  | 2019-09-30 | [8 empty] | SI Civil | 2019-05-01 | 2019-09-13 | [9 empty] | 200 | SI Elect | 2019-05-01 | 2019-09-30 | [9 empty] | 200
Project Name 169 | Project Number169 | Project Manager169 | Program Manager169 | Construction | Location169 | SI | Contact169 | TRUE |  | 2019-03-04 | 2019-03-04 | 2019-09-26 | 2019-09-26 | 2019-04-23 |  | 2019-09-26 |  | 1288000 | 1288000 |  | SI Elect | 2019-03-04 | 2019-09-26 | 2019-03-04 | 2019-09-26 | 2019-04-23 | 2019-09-26 |  |  | 170000 | 170000 |  | 1500 | SI Civil | 2019-03-04 | 2019-09-26 | 2019-03-04 | 2019-09-26 | 2019-04-23 | 2019-09-26 |  |  | 752000 | 752000 |  | 2160 | SI Line | 2019-03-04 | 2019-09-26 | [9 empty] | 712
Project Name 170 | Project Number170 | Project Manager170 | Program Manager170 | Pre-Construction | Location170 | NI | Contact170 | FALSE | 2700 | 2019-05-01 |  | 2019-06-28 | [8 empty] | NI Line
Project Name 171 | Project Number171 | Project Manager171 | Program Manager171 | Completion | Location171 | NI | Contact171 | TRUE | 2860 | 2019-02-01 | 2019-02-01 | 2019-03-04 | 2019-03-04 | 2019-02-01 | 2019-01-25 | 2019-03-04 | 2019-03-04 | 573385 | 510907 |  | NI Line
Project Name 172 | Project Number172 | Project Manager172 | Program Manager172 | Completion | Location172 | NI | Contact172 | FALSE | 1914 | 2019-01-14 | 2019-01-14 | 2019-02-28 | 2019-02-28 | 2019-01-14 | 2019-01-07 | 2019-03-15 | 2019-03-15 | 201500 | 148988 |  | NI Elect
Project Name 173 | Project Number173 | Project Manager173 | Program Manager173 | Completion | Location173 | VI | Contact173 | TRUE | 480 | 2019-02-04 | 2019-02-04 | 2019-03-12 | 2019-03-12 |  | 2019-02-04 | 2019-03-12 |  | 214624 | 190145 |  | VI Civil
Project Name 174 | Project Number174 | Project Manager174 | Program Manager174 | Completion | Location174 | VI | Contact174 | FALSE | 250 | 2019-03-13 | 2019-03-13 | 2019-04-02 | 2019-04-02 | 2019-03-13 | 2019-03-13 | 2019-04-02 | 2019-04-02 |  |  | 48500 | VI Civil
Project Name 175 | Project Number175 | Project Manager175 | Program Manager175 | Completion | Location175 | VI | Contact175 | FALSE | 1245 | 2019-05-01 | 2019-05-01 | 2019-07-01 | 2019-07-01 | 2019-05-01 | 2019-03-11 | 2019-07-26 | 2019-04-04 | 138805 | 82485 |  | VI Civil
Project Name 176 | Project Number176 | Project Manager176 | Program Manager176 | Pre-Construction | Location176 | NI | Contact176 | TRUE | 5750 | 2019-06-03 |  | 2019-08-09 | [5 empty] | 1753000 | 1753000 |  | NI Civil
Project Name 177 | Project Number177 | Project Manager177 | Program Manager177 | Completion | Location177 | SI | Contact177 | FALSE | 450 | 2019-02-25 | 2019-02-25 | 2019-03-15 | 2019-03-15 | 2019-02-25 | 2019-02-25 | 2019-03-15 | 2019-03-15 | 71456 | 71456 | 71456 | SI MASS (SS)
Project Name 178 | Project Number178 | Project Manager178 | Program Manager178 | Construction | Location178 | SI | Contact178 | TRUE | 360 | 2019-02-04 | 2019-02-04 | 2019-05-11 | 2019-05-11 | 2019-02-04 | 2019-02-04 | 2019-05-11 |  | 48622 | 48622 |  | SI MASS (SS)
Project Name 179 | Project Number179 | Project Manager179 | Program Manager179 | Construction | Location179 | SI | Contact179 | FALSE | 250 | 2018-09-04 | 2018-09-04 |  | 2018-12-01 | 2018-09-04 | 2018-09-04 | 2019-05-17 |  | 27835 | 27835 |  | SI Elect
Project Name 180 | Project Number180 | Project Manager180 | Program Manager180 | Completion | Location180 | SI | Contact180 | FALSE | 150 | 2019-01-07 | 2019-01-07 | 2019-01-18 | 2019-01-18 | 2019-02-19 | 2019-02-19 | 2019-03-01 | 2019-03-01 | 20000 | 20000 |  | SI Elect
Project Name 181 | Project Number181 | Project Manager181 | Program Manager181 | Construction | Location181 | VI | Contact181 | TRUE | 2902 | 2018-09-01 | 2018-09-01 | 2018-11-30 | 2018-11-30 | 2018-09-01 | 2018-09-01 | 2019-07-05 |  | 383034 | 350927 |  | LM Line | [15 empty] | 2018-09-01 | 2018-11-30 | 2018-09-01 | 2019-07-05 |  | 2018-09-01
Project Name 182 | Project Number182 | Project Manager182 | Program Manager182 | Completion | Location182 | VI | Contact182 | TRUE |  | 2019-01-15 | 2019-01-02 | 2019-03-30 | 2019-03-31 | 2019-01-03 | 2019-01-03 | 2019-03-31 | 2019-03-31 | 364998 | 342062 |  | VI Line
Project Name 183 | Project Number183 | Project Manager183 | Program Manager183 | Completion | Location183 | LM | Contact183 | FALSE |  |  | 2016-05-09 |  | 2017-03-31 |  | 2016-05-16 | 2019-01-31 | 2019-02-14 | 943903 | 2640832 |  | LM Line
Project Name 184 | Project Number184 | Project Manager184 | Program Manager184 | Construction | Location184 | LM | Contact184 | FALSE |  | 2018-11-20 | 2018-11-20 | 2019-03-08 | 2019-03-08 | 2018-11-20 | 2018-11-20 | 2019-06-28 |  | 471484 | 381415 |  | LM Civil | 2018-11-20 | 2018-12-12 | 2018-11-20 | 2018-12-12 | 2018-11-20 | 2018-12-12 | 2018-11-20 | 2018-12-14 | 171998 |  |  | 836 | LM Field Mech | 2018-12-13 | 2019-01-11 | 2018-12-13 | 2019-01-11 | 2018-12-13 |  | 2018-12-21 | 2018-12-10 | 147592 |  |  | 291.5 | LM Line | 2019-01-14 | 2019-03-08 | 2019-01-14 | 2019-03-08 | 2019-01-14 | 2019-06-28 | 2019-01-25 |  | 97831 |  |  | 940 | LM Elect1 | 2019-01-28 | 2019-02-08 | 2019-01-28 | 2019-02-08 | 2019-03-11 | 2019-04-05 | 2019-03-11 |  | 54063 |  |  | 586.5
Project Name 185 | Project Number185 | Project Manager185 | Program Manager185 | Construction | Location185 | LM | Contact185 | FALSE |  | 2018-11-12 | 2018-11-12 | 2019-03-31 | 2019-03-31 | 2018-11-12 | 2018-11-12 | 2019-07-31 |  | 322084 | 231346 |  | LM Civil | 2018-11-12 | 2018-11-14 | 2018-11-12 | 2018-11-14 | 2018-11-12 | 2018-11-14 | 2018-11-12 | 2018-11-14 | 16051 |  |  | 190 | LM Field Mech | 2018-11-28 | 2018-12-07 | 2018-11-28 | 2018-12-07 | 2018-11-28 | 2018-12-07 | 2018-12-07 | 2018-11-28 | 160410 |  |  | 326.5 | LM Line | 2018-12-10 | 2018-12-21 | 2018-12-10 | 2018-12-21 | 2018-12-10 | 2019-01-25 | 2019-01-10 | 2019-01-25 | 97831 |  |  | 940 | LM Elect1 | 2019-01-07 | 2019-01-25 | 2019-01-07 | 2019-01-25 | 2019-01-07 | 2019-03-01 | 2019-02-20 |  | 47792 |  |  | 493
Project Name 186 | Project Number186 | Project Manager186 | Program Manager186 | Completion | Location186 | VI | Contact186 | FALSE |  |  | 2018-04-01 |  | 2018-08-02 | 2018-04-01 | 2018-04-03 | 2018-09-15 | 2019-03-29 | 190047 | 160657 |  | VI Elect
Project Name 187 | Project Number187 | Project Manager187 | Program Manager187 | Completion | Location187 | SI | Contact187 | FALSE |  |  | 2018-04-01 |  | 2018-08-31 | 2018-06-13 | 2018-09-24 | 2018-12-20 | 2018-11-30 | 437689 | 437689 | 347919 | SI Line
Project Name 188 | Project Number188 | Project Manager188 | Program Manager188 | Completion | Location188 | SI | Contact188 | FALSE |  |  | 2018-08-15 |  | 2018-09-15 |  | 2018-10-09 | 2018-11-16 | 2018-11-21 | 225236 | 180000 | 125000 | SI Line
Project Name 189 | Project Number189 | Project Manager189 | Program Manager189 | Completion | Location189 | SI | Contact189 | FALSE | 1200 | 2018-12-03 | 2019-01-14 | 2019-01-31 | 2019-03-31 | 2019-01-14 | 2018-11-30 | 2019-03-31 | 2019-01-31 | 110000 | 110000 | 103078 | SI Line
Project Name 190 | Project Number190 | Project Manager190 | Program Manager190 | Pre-Construction | Location190 | SI | Contact190 | FALSE | 6000 | 2019-08-01 |  | 2020-03-31 | [8 empty] | SI Line
Project Name 191 | Project Number191 | Project Manager191 | Program Manager191 | Pre-Construction | Location191 | SI | Contact191 | FALSE | 6500 | 2019-04-15 | 2019-04-15 | 2019-10-31 | 2019-11-30 | 2019-04-15 |  | 2019-11-30 |  | 997000 | 997000 |  | SI Line
Project Name 192 | Project Number192 | Project Manager192 | Program Manager192 | Pre-Construction | Location192 | SI | Contact192 | FALSE | 8000 | 2019-09-01 |  | 2020-05-31 | [8 empty] | SI Line
Project Name 193 | Project Number193 | Project Manager193 | Program Manager193 | Pre-Construction | Location193 | SI | Contact193 | FALSE | 5000 | 2019-09-30 |  | 2020-10-30 | [8 empty] | SI Line
Project Name 194 | Project Number194 | Project Manager194 | Program Manager194 | Pre-Construction | Location194 | SI | Contact194 | FALSE | 10000 | 2019-04-15 |  | 2020-10-31 | [8 empty] | SI Line
Project Name 195 | Project Number195 | Project Manager195 | Program Manager195 | Pre-Construction | Location195 | SI | Contact195 | FALSE | 3000 | 2020-07-01 |  | 2020-09-01 | [8 empty] | SI Line
Project Name 196 | Project Number196 | Project Manager196 | Program Manager196 | Pre-Construction | Location196 | SI | Contact196 | FALSE | 30000 | 2022-02-14 |  | 2025-12-19 | [8 empty] | SI Line
Project Name 197 | Project Number197 | Project Manager197 | Program Manager197 | Pre-Construction | Location197 | LM | Contact197 | FALSE | 550 | 2019-04-15 | 2019-04-15 | 2019-05-17 | 2019-05-17 | 2019-04-15 |  | 2019-05-17 |  | 62390 | 62390 |  | LM Elect2
Project Name 198 | Project Number198 | Project Manager198 | Program Manager198 | Completion | Location198 | VI | Contact198 | TRUE | 600 | 2019-02-04 | 2019-02-04 | 2019-02-25 | 2019-02-25 | 2019-02-04 | 2019-02-04 | 2019-02-28 | 2019-02-28 | 160354 | 185648 |  | LM Winders
Project Name 199 | Project Number199 | Project Manager199 | Program Manager199 | Completion | Location199 | LM | Contact199 | FALSE | 922 | 2018-10-01 | 2018-11-05 | 2018-12-31 | 2018-12-31 |  | 2018-11-05 | 2019-01-31 | 2019-04-05 | 87062 | 114870 |  | LM Elect2
Project Name 200 | Project Number200 | Project Manager200 | Program Manager200 | Completion | Location200 | VI | Contact200 | FALSE | 790 | 2018-12-10 | 2018-12-10 | 2019-03-15 | 2019-03-15 | 2018-12-10 | 2018-12-10 | 2019-03-15 | 2019-03-15 | 70340 | 30739 |  | VI Civil
Project Name 201 | Project Number201 | Project Manager201 | Program Manager201 | Cancelled | Location201 | VI | Contact201 | FALSE |  | 2019-04-01 |  | 2019-08-01 | [5 empty] | 291273 | 291273 | [14 empty] | VI Civil | 2019-04-15 | [7 empty] | 291273 | 291273
Project Name 202 | Project Number202 | Project Manager202 | Program Manager202 | Completion | Location202 | LM | Contact202 | TRUE | 450 | 2019-01-07 | 2018-12-07 | 2019-01-28 | 2019-02-08 | 2018-12-07 | 2019-01-07 | 2019-02-08 | 2019-02-01 | 73556 | 73556 | 52918 | VI Elect
Project Name 203 | Project Number203 | Project Manager203 | Program Manager203 | Completion | Location203 | SI | Contact203 | TRUE | 940 | 2019-02-11 | 2019-02-11 | 2019-03-15 | 2019-03-01 | 2019-02-11 | 2019-02-11 | 2019-03-01 | 2019-03-01 | 157000 | 124554 | 124554 | SI MASS (SS)
Project Name 204 | Project Number204 | Project Manager204 | Program Manager204 | Pre-Construction | Location204 | NI | Contact204 | FALSE | 20000 | 2021-04-01 |  | 2023-07-01 | [8 empty] | NI Elect
Project Name 205 | Project Number205 | Project Manager205 | Program Manager205 | Completion | Location205 | VI | Contact205 | FALSE |  |  | 2018-08-07 |  | 2018-11-30 | 2018-08-17 | 2018-08-27 | 2019-03-29 | 2019-03-15 | 278400 | 266059 |  | VI Elect
Project Name 206 | Project Number206 | Project Manager206 | Program Manager206 | Completion | Location206 | SI | Contact206 | TRUE | 632 | 2019-03-04 | 2019-03-04 | 2019-03-20 | 2019-03-20 | 2019-03-04 | 2019-03-04 | 2019-03-20 | 2019-03-18 | 83718 | 83718 |  | LM Winders
Project Name 207 | Project Number207 | Project Manager207 | Program Manager207 | Completion | Location207 | NI | Contact207 | TRUE | 1767 | 2018-10-01 | 2018-10-09 | 2019-01-20 | 2018-11-15 |  | 2018-10-09 | 2019-01-18 | 2019-01-11 | 229452 | 218735 | 243689 | NI Civil
Project Name 208 | Project Number208 | Project Manager208 | Program Manager208 | Completion | Location208 | VI | Contact208 | FALSE |  | 2018-05-29 | 2018-05-29 | 2018-08-04 | 2018-06-14 |  | 2018-06-04 |  | 2018-07-24 | 0 |  | 46376 | VI Elect
Project Name 209 | Project Number209 | Project Manager209 | Program Manager209 | Cancelled | Location209 | NI | Contact209 | FALSE |  | 2019-05-01 | [10 empty] | NI Elect
Project Name 210 | Project Number210 | Project Manager210 | Program Manager210 | Completion | Location210 | SI | Contact210 | TRUE | 390 |  | 2018-11-22 |  | 2018-11-30 | 2019-01-21 | 2019-01-21 | 2019-02-01 | 2019-02-01 | 53000 | 53000 | 53000 | SI MASS (SS)
Project Name 211 | Project Number211 | Project Manager211 | Program Manager211 | Completion | Location211 | SI | Contact211 | TRUE | 550 | 2019-01-21 | 2019-01-21 | 2019-02-08 | 2019-02-08 | 2019-01-21 | 2019-01-21 | 2019-02-08 | 2019-02-08 | 122000 | 100000 | 100000 | SI MASS (SS)
Project Name 212 | Project Number212 | Project Manager212 | Program Manager212 | Completion | Location212 | VI | Contact212 | FALSE |  |  | 2018-09-17 |  | 2018-10-05 | 2018-11-13 |  | 2018-12-17 | 2018-12-13 | 100576 | 0 | 0 | VI Civil
Project Name 213 | Project Number213 | Project Manager213 | Program Manager213 | Completion | Location213 | LM | Contact213 | FALSE |  |  | 2017-11-06 |  | 2018-10-19 |  | 2017-11-06 |  | 2018-10-19 | 602744 |  | 389969 | LM Civil
Project Name 214 | Project Number214 | Project Manager214 | Program Manager214 | Cancelled | Location214 | LM | Contact214 | TRUE |  |  | 2018-10-10 |  | 2019-03-31 |  | 2018-10-30 | 2019-03-31 |  | 0 |  |  | LM Civil
Project Name 215 | Project Number215 | Project Manager215 | Program Manager215 | Completion | Location215 | VI | Contact215 | TRUE |  |  | 2017-02-15 |  | 2018-10-31 |  | 2017-02-15 | 2018-10-30 | 2018-10-25 | 9485299 | 6902540 |  | VI Line
Project Name 216 | Project Number216 | Project Manager216 | Program Manager216 | Completion | Location216 | LM | Contact216 | FALSE |  | 2018-08-07 | 2018-08-07 | 2018-10-30 | 2018-10-30 | 2018-08-07 | 2018-08-07 | 2018-10-30 | 2018-11-09 | 295255 | 232050 | 232050 | LM Elect1
Project Name 217 | Project Number217 | Project Manager217 | Program Manager217 | Completion | Location217 | SI | Contact217 | FALSE | 150 | 2019-01-08 | 2019-01-08 | 2019-01-18 | 2019-01-18 | 2019-01-08 | 2019-01-08 | 2019-01-11 | 2019-01-11 | 20000 | 20000 |  | SI Elect
Project Name 218 | Project Number218 | Project Manager218 | Program Manager218 | Completion | Location218 | SI | Contact218 | FALSE | 360 | 2018-10-01 | 2018-10-01 | 2018-12-21 | 2018-12-21 | 2018-10-01 | 2018-10-22 | 2019-01-18 | 2019-01-18 | 28000 | 28000 | 30728 | SI Elect
Project Name 219 | Project Number219 | Project Manager219 | Program Manager219 | Pre-Construction | Location219 | VI | Contact219 | FALSE |  | 2019-06-19 |  | 2019-07-19 | [8 empty] | LM Line
Project Name 220 | Project Number220 | Project Manager220 | Program Manager220 | Pre-Construction | Location220 | VI | Contact220 | FALSE |  | 2019-05-01 |  | 2019-06-30 | [8 empty] | LM Line
Project Name 221 | Project Number221 | Project Manager221 | Program Manager221 | Pre-Construction | Location221 | NI | Contact221 | FALSE | 100 | 2020-04-01 |  | 2020-05-30 | [8 empty] | NI Elect
Project Name 222 | Project Number222 | Project Manager222 | Program Manager222 | Pre-Construction | Location222 | LM | Contact222 | FALSE |  | 2019-06-03 |  | 2019-06-14 | [8 empty] | LM Line
Project Name 223 | Project Number223 | Project Manager223 | Program Manager223 | Completion | Location223 | VI | Contact223 | FALSE |  | 2019-01-09 | 2019-01-09 | 2019-02-06 | 2019-01-31 | 2019-01-09 | 2019-01-09 | 2019-01-31 | 2019-01-31 | 143412 | 150000 |  | LM Winders
Project Name 224 | Project Number224 | Project Manager224 | Program Manager224 | Pre-Construction | Location224 | NI | Contact224 | FALSE | 6000 | 2021-09-01 |  | 2022-03-31 | [8 empty] | NI Elect
Project Name 225 | Project Number225 | Project Manager225 | Program Manager225 | Pre-Construction | Location225 | SI | Contact225 | FALSE | 200 | 2018-12-03 |  | 2018-12-21
Project Name 226 | Project Number226 | Project Manager226 | Program Manager226 | Completion | Location226 | SI | Contact226 | FALSE | 1776 | 2018-10-29 | 2018-10-29 | 2018-12-13 | 2018-12-13 | 2018-10-29 | 2018-10-29 | 2018-12-13 | 2018-12-13 | 472000 | 472000 | 290000 | SI Civil
Project Name 227 | Project Number227 | Project Manager227 | Program Manager227 | Pre-Construction | Location227 | SI | Contact227 | FALSE | 600 | 2019-01-14 |  | 2019-03-22 | [8 empty] | SI Civil
Project Name 228 | Project Number228 | Project Manager228 | Program Manager228 | Completion | Location228 | LM | Contact228 | TRUE | 1301 | 2018-11-13 | 2018-11-13 | 2018-12-14 | 2018-12-14 | 2018-11-13 | 2018-11-13 | 2018-12-14 | 2018-12-07 | 113313 | 113313 | 109319 | LM Winders
Project Name 229 | Project Number229 | Project Manager229 | Program Manager229 | Completion | Location229 | NI | Contact229 | FALSE | 352 | 2018-11-19 | 2018-11-19 | 2018-11-23 | 2018-11-23 | 2018-11-19 | 2018-11-19 | 2018-11-23 | 2018-11-23 | 36080 | 36080 | 34636 | NI Elect
Project Name 230 | Project Number230 | Project Manager230 | Program Manager230 | Completion | Location230 | NI | Contact230 | FALSE | 447 | 2018-11-12 | 2018-11-12 | 2018-11-23 | 2018-11-23 | 2018-11-12 | 2018-11-12 | 2018-11-23 | 2018-11-23 | 52301 | 52301 | 47043 | NI Civil
Project Name 231 | Project Number231 | Project Manager231 | Program Manager231 | Cancelled | Location231 | SI | Contact231 | FALSE |  | 2019-08-01 |  | 2019-09-30 | [8 empty] | SI Elect
Project Name 232 | Project Number232 | Project Manager232 | Program Manager232 | Completion | Location232 | LM | Contact232 | FALSE |  | 2019-01-07 | 2019-01-07 | 2020-02-28 | 2019-02-28 | 2019-01-07 | 2019-01-07 | 2019-02-28 | 2019-02-21 | 87187 | 77115 |  | LM Elect2
Project Name 233 | Project Number233 | Project Manager233 | Program Manager233 | Construction | Location233 | VI | Contact233 | FALSE |  |  | 2018-09-15 |  | 2018-10-31 |  | 2018-09-14 |  | 2018-11-02 | 325000 | 344000 | 344022 | LM Field Mech |  |  | 2018-09-15 | 2018-10-31 | 2018-09-15 |  | 2018-09-14 | 2018-11-02 |  |  |  | 1470 | LM Elect1 |  |  | 2018-10-09 | 2018-10-19 | 2018-10-09 |  | 2018-11-01 | 2018-10-09 |  |  |  | 266
Project Name 234 | Project Number234 | Project Manager234 | Program Manager234 | Completion | Location234 | NI | Contact234 | TRUE | 3927 | 2018-08-13 | 2018-08-13 | 2018-10-13 | 2018-10-13 |  | 2018-09-24 | 2019-01-25 | 2019-01-31 | 403483 | 602530 |  | NI Line
Project Name 235 | Project Number235 | Project Manager235 | Program Manager235 | Cancelled | Location235 | VI | Contact235 | FALSE |  |  | 2019-02-15 |  | 2019-03-15 |  |  |  | 2018-10-24 | 42445 | 0 | 0 | VI Civil
Project Name 236 | Project Number236 | Project Manager236 | Program Manager236 | Completion | Location236 | VI | Contact236 | TRUE |  |  | 2017-02-15 |  | 2018-10-31 |  | 2017-02-15 | 2018-10-31 | 2018-10-31 | 9485299 | 6902540 |  | VI Line
Project Name 237 | Project Number237 | Project Manager237 | Program Manager237 | Completion | Location237 | NI | Contact237 | FALSE |  |  | 2018-05-14 |  | 2018-11-20 |  | 2018-05-14 | 2018-11-20 | 2018-11-20 | 733362 | 727352 |  | NI Elect
Project Name 238 | Project Number238 | Project Manager238 | Program Manager238 | Completion | Location238 | LM | Contact238 | FALSE |  |  | 2016-07-04 |  | 2016-07-18 |  | 2016-07-07 |  | 2016-07-20 |  | 120069 |  | LM Field Mech
Project Name 239 | Project Number239 | Project Manager239 | Program Manager239 | Completion | Location239 | LM | Contact239 | FALSE |  |  | 2017-10-16 |  | 2017-10-21 |  | 2017-10-20 |  | 2017-11-30 |  |  | 284000 | LM Field Mech
Project Name 240 | Project Number240 | Project Manager240 | Program Manager240 | Completion | Location240 | SI | Contact240 | TRUE |  |  | 2018-04-16 |  | 2018-05-09 |  | 2018-04-16 |  | 2018-05-05 | 203000 |  | 175000 | SI MASS (SS)
Project Name 241 | Project Number241 | Project Manager241 | Program Manager241 | Completion | Location241 | VI | Contact241 | FALSE |  |  | 2016-07-20 |  | 2016-12-31 |  | 2016-08-02 |  | 2017-03-31 | 171218 |  | 87400 | LM Field Mech
Project Name 242 | Project Number242 | Project Manager242 | Program Manager242 | Completion | Location242 | SI | Contact242 | FALSE |  |  | 2017-07-17 |  | 2017-07-29 | 2017-07-17 | 2017-07-17 |  | 2017-08-04 | 40770 |  |  | LM Winders
Project Name 243 | Project Number243 | Project Manager243 | Program Manager243 | Completion | Location243 | SI | Contact243 | FALSE |  |  | 2017-08-14 |  | 2017-08-29 | 2017-08-14 | 2017-09-11 |  | 2017-09-25 | 91553 |  |  | LM Winders
Project Name 244 | Project Number244 | Project Manager244 | Program Manager244 | Completion | Location244 | SI | Contact244 | FALSE |  |  | 2017-06-26 |  | 2017-09-23 | 2017-06-26 | 2017-06-26 |  | 2017-08-29 | 91553 |  |  | LM Winders
Project Name 245 | Project Number245 | Project Manager245 | Program Manager245 | Completion | Location245 | SI | Contact245 | FALSE |  |  | 2017-09-11 |  | 2017-09-20 |  | 2017-09-11 |  | 2017-09-20 | 59000 |  | 55000 | SI MASS (MECH)
Project Name 246 | Project Number246 | Project Manager246 | Program Manager246 | Completion | Location246 | SI | Contact246 | FALSE |  |  | 2016-05-02 |  | 2016-12-23 |  | 2016-05-02 |  | 2017-12-04 | 3386000 |  | 5216879 | SI MASS (MECH)
Project Name 247 | Project Number247 | Project Manager247 | Program Manager247 | Completion | Location247 | SI | Contact247 | FALSE |  |  | 2017-01-09 |  | 2017-12-01 |  | 2017-01-09 |  | 2017-12-01 | 467000 |  | 774263 | SI MASS (MECH)
Project Name 248 | Project Number248 | Project Manager248 | Program Manager248 | Completion | Location248 | SI | Contact248 | FALSE |  |  | 2017-11-20 |  | 2017-12-14 |  | 2017-11-20 |  | 2017-12-14 | 150000 |  | 100000 | SI MASS (MECH)
Project Name 249 | Project Number249 | Project Manager249 | Program Manager249 | Completion | Location249 | SI | Contact249 | FALSE |  |  | 2018-02-05 |  | 2018-05-18 |  | 2018-02-05 |  | 2018-05-18 | 331000 |  | 277000 | SI MASS (MECH)
Project Name 250 | Project Number250 | Project Manager250 | Program Manager250 | Completion | Location250 | SI | Contact250 | FALSE |  |  | 2017-10-30 |  | 2017-11-17 |  | 2017-10-30 |  | 2017-11-17 | 80000 |  | 69000 | SI MASS (MECH)
Project Name 251 | Project Number251 | Project Manager251 | Program Manager251 | Completion | Location251 | SI | Contact251 | FALSE |  |  | 2017-03-27 |  | 2017-04-07 |  | 2017-03-27 |  | 2017-04-03 | 98000 |  | 84190 | SI MASS (SS)
Project Name 252 | Project Number252 | Project Manager252 | Program Manager252 | Completion | Location252 | LM | Contact252 | FALSE |  |  | 2018-03-30 |  | 2018-04-15 |  | 2018-03-30 |  | 2018-04-15 | 112000 |  | 86195 | LM Field Mech
Project Name 253 | Project Number253 | Project Manager253 | Program Manager253 | Completion | Location253 | NI | Contact253 | TRUE |  |  | 2018-05-29 |  | 2018-08-16 |  | 2018-06-12 |  | 2018-08-31 | 398976 |  | 498920 | LM Field Mech
Project Name 254 | Project Number254 | Project Manager254 | Program Manager254 | Completion | Location254 | LM | Contact254 | FALSE |  |  | 2015-09-15 |  | 2015-09-27 |  | 2015-09-15 |  | 2017-10-01 |  |  | 168302 | LM Field Mech
Project Name 255 | Project Number255 | Project Manager255 | Program Manager255 | Completion | Location255 | LM | Contact255 | TRUE |  |  | 2018-02-19 |  | 2018-03-31 | 2018-02-19 | 2018-02-19 | 2018-05-27 |  | 403143 |  | 508036 | LM Elect1
Project Name 256 | Project Number256 | Project Manager256 | Program Manager256 | Completion | Location256 | SI | Contact256 | TRUE |  |  | 2018-03-19 |  | 2018-04-06 |  | 2018-03-19 |  | 2018-04-06 | 146000 |  | 123000 | SI MASS (SS)
Project Name 257 | Project Number257 | Project Manager257 | Program Manager257 | Completion | Location257 | LM | Contact257 | TRUE |  |  | 2018-04-15 |  | 2018-05-03 |  | 2018-04-15 |  | 2018-05-03 | 200000 |  | 180123 | LM Field Mech
Project Name 258 | Project Number258 | Project Manager258 | Program Manager258 | Completion | Location258 | LM | Contact258 | TRUE |  |  | 2018-01-02 |  | 2018-02-03 |  | 2018-01-02 |  | 2018-03-09 | 120000 |  | 108000 | LM Field Mech
Project Name 259 | Project Number259 | Project Manager259 | Program Manager259 | Completion | Location259 | SI | Contact259 | TRUE |  |  | 2018-05-14 |  | 2018-06-15 |  | 2018-05-14 |  | 2018-06-15 | 179000 |  | 124000 | SI MASS (SS)
Project Name 260 | Project Number260 | Project Manager260 | Program Manager260 | Completion | Location260 | SI | Contact260 | FALSE |  |  | 2018-02-19 |  | 2018-03-14 |  | 2018-02-19 |  | 2018-03-09 | 140000 |  | 93000 | SI MASS (MECH)
Project Name 261 | Project Number261 | Project Manager261 | Program Manager261 | Completion | Location261 | SI | Contact261 | FALSE |  |  | 2017-04-03 |  | 2017-05-19 |  | 2017-04-03 |  | 2017-05-18 | 107000 |  | 73771 | SI MASS (SS)
Project Name 262 | Project Number262 | Project Manager262 | Program Manager262 | Completion | Location262 | SI | Contact262 | FALSE |  |  | 2017-08-14 |  | 2017-09-01 |  | 2017-08-14 |  | 2017-09-01 | 260000 |  | 275000 | SI MASS (MECH)
Project Name 263 | Project Number263 | Project Manager263 | Program Manager263 | Completion | Location263 | SI | Contact263 | FALSE |  |  | 2017-01-09 |  | 2017-03-31 |  | 2017-01-09 |  | 2017-07-21 | 786000 |  | 877000 | SI MASS (MECH)
Project Name 264 | Project Number264 | Project Manager264 | Program Manager264 | Completion | Location264 | VI | Contact264 | TRUE |  |  | 2017-08-14 |  | 2017-09-08 |  | 2017-08-14 |  | 2017-09-15 | 418000 |  | 430000 | LM Field Mech
Project Name 265 | Project Number265 | Project Manager265 | Program Manager265 | Completion | Location265 | SI | Contact265 | FALSE |  |  | 2017-06-19 |  | 2017-07-25 |  | 2017-06-19 |  | 2017-09-08 | 218000 |  | 286000 | SI MASS (SS)
Project Name 266 | Project Number266 | Project Manager266 | Program Manager266 | Completion | Location266 | LM | Contact266 | TRUE |  |  | 2018-04-03 |  | 2018-04-30 |  | 2018-04-03 |  | 2018-04-23 | 310000 |  | 284384 | LM Field Mech
Project Name 267 | Project Number267 | Project Manager267 | Program Manager267 | Completion | Location267 | LM | Contact267 | TRUE |  |  | 2018-05-05 |  | 2018-06-01 |  | 2018-04-29 |  | 2018-05-18 | 308000 |  | 271000 | LM Field Mech
Project Name 268 | Project Number268 | Project Manager268 | Program Manager268 | Completion | Location268 | SI | Contact268 | FALSE |  |  | 2017-10-10 |  | 2017-10-20 |  | 2017-10-10 |  | 2017-10-17 | 38000 |  | 38000 | SI MASS (SS)
Project Name 269 | Project Number269 | Project Manager269 | Program Manager269 | Completion | Location269 | SI | Contact269 | TRUE |  |  | 2017-10-24 |  | 2018-01-25 |  | 2017-10-02 | 2018-02-09 | 2018-02-13 | 974000 | 1266417 |  | SI MASS (SS)
Project Name 270 | Project Number270 | Project Manager270 | Program Manager270 | Completion | Location270 | SI | Contact270 | FALSE |  |  | 2017-04-24 |  | 2017-05-05 |  | 2017-04-24 |  | 2017-05-03 | 135000 |  | 186000 | SI MASS (SS)
Project Name 271 | Project Number271 | Project Manager271 | Program Manager271 | Completion | Location271 | LM | Contact271 | TRUE |  |  | 2016-10-25 |  | 2017-03-31 |  | 2016-12-22 |  | 2017-05-15 | 416847 |  | 377923 | LM Field Mech
Project Name 272 | Project Number272 | Project Manager272 | Program Manager272 | Completion | Location272 | SI | Contact272 | FALSE |  |  | 2017-06-19 |  | 2017-07-07 |  | 2017-06-19 |  | 2017-07-07 | 475000 |  | 527000 | SI MASS (SS)
Project Name 273 | Project Number273 | Project Manager273 | Program Manager273 | Completion | Location273 | SI | Contact273 | FALSE |  |  | 2017-07-10 |  | 2017-08-04 |  | 2017-07-10 |  | 2017-08-04 | 184000 |  | 163000 | SI MASS (SS)
Project Name 274 | Project Number274 | Project Manager274 | Program Manager274 | Completion | Location274 | NI | Contact274 | TRUE |  |  |  | 2018-06-18 | 2018-06-22 |  | 2018-05-28 |  | 2018-06-14 | 120000 | 120000 |  | LM Winders
Project Name 275 | Project Number275 | Project Manager275 | Program Manager275 | Completion | Location275 | SI | Contact275 | TRUE |  |  | 2018-02-26 |  | 2018-03-07 |  | 2018-02-26 |  | 2018-03-07 | 113000 |  | 102000 | SI MASS (SS)
Project Name 276 | Project Number276 | Project Manager276 | Program Manager276 | Completion | Location276 | SI | Contact276 | TRUE |  |  | 2017-10-30 |  | 2017-11-11 |  | 2017-10-30 |  | 2017-11-25 | 102000 |  | 128000 | LM Winders
Project Name 277 | Project Number277 | Project Manager277 | Program Manager277 | Completion | Location277 | SI | Contact277 | FALSE |  |  | 2017-04-10 |  | 2017-05-12 |  | 2017-04-10 |  | 2017-05-18 | 90000 |  | 102809 | SI MASS (SS)
Project Name 278 | Project Number278 | Project Manager278 | Program Manager278 | Completion | Location278 | SI | Contact278 | FALSE |  |  | 2017-08-28 |  | 2017-10-06 |  | 2017-08-28 |  | 2017-10-06 | 230000 |  | 197000 | SI MASS (SS)
Project Name 279 | Project Number279 | Project Manager279 | Program Manager279 | Completion | Location279 | SI | Contact279 | FALSE |  |  | 2017-09-25 |  | 2017-10-19 |  | 2017-09-25 |  | 2017-10-13 | 111000 |  | 72000 | SI MASS (MECH)
Project Name 280 | Project Number280 | Project Manager280 | Program Manager280 | Completion | Location280 | SI | Contact280 | TRUE |  | 2018-04-16 |  | 2018-05-04 |  |  | 2018-08-07 |  | 2018-08-24 | 115600 | 115600 |  | LM Winders
Project Name 281 | Project Number281 | Project Manager281 | Program Manager281 | Completion | Location281 | SI | Contact281 | TRUE |  |  | 2018-08-07 |  | 2018-09-13 |  | 2018-08-07 |  | 2018-09-13 | 261000 |  | 240000 | SI MASS (SS)
Project Name 282 | Project Number282 | Project Manager282 | Program Manager282 | Completion | Location282 | SI | Contact282 | TRUE |  | 2018-05-14 |  | 2018-06-06 |  |  | 2018-07-09 |  | 2018-07-27 | 115600 | 115600 |  | LM Winders
Project Name 283 | Project Number283 | Project Manager283 | Program Manager283 | Completion | Location283 | SI | Contact283 | TRUE |  |  | 2018-07-03 |  | 2018-08-03 |  | 2018-07-03 |  | 2018-08-03 | 187000 |  | 170000 | SI MASS (SS)
Project Name 284 | Project Number284 | Project Manager284 | Program Manager284 | Completion | Location284 | SI | Contact284 | TRUE |  |  | 2018-06-19 |  | 2018-06-27 |  | 2018-06-19 |  | 2018-06-24 | 69000 |  | 48000 | SI MASS (SS)
Project Name 285 | Project Number285 | Project Manager285 | Program Manager285 | Completion | Location285 | LM | Contact285 | TRUE |  |  | 2017-08-07 |  | 2017-09-01 |  | 2017-08-28 |  | 2017-11-14 | 548000 |  | 600000 | LM Field Mech
Project Name 286 | Project Number286 | Project Manager286 | Program Manager286 | Completion | Location286 | SI | Contact286 | TRUE |  |  | 2018-04-09 |  | 2018-04-13 |  | 2018-04-09 |  | 2018-04-13 | 17453 |  | 13000 | SI MASS (SS)
Project Name 287 | Project Number287 | Project Manager287 | Program Manager287 | Completion | Location287 | LM | Contact287 | TRUE |  |  | 2017-09-11 |  | 2017-09-20 |  | 2017-09-11 |  | 2017-09-20 | 82792 |  | 26000 | LM Field Mech
Project Name 288 | Project Number288 | Project Manager288 | Program Manager288 | Completion | Location288 | SI | Contact288 | TRUE |  |  | 2018-05-22 |  | 2018-07-12 |  | 2018-05-22 |  | 2018-09-07 | 390000 |  | 350000 | SI MASS (MECH)
Project Name 289 | Project Number289 | Project Manager289 | Program Manager289 | Completion | Location289 | SI | Contact289 | TRUE |  |  |  |  | 2018-05-13 |  | 2018-04-30 |  | 2018-05-12 | 90658 |  | 88000 | LM Winders
Project Name 290 | Project Number290 | Project Manager290 | Program Manager290 | Completion | Location290 | SI | Contact290 | TRUE |  |  | 2018-09-25 |  | 2018-11-02 |  | 2018-09-25 | 2018-11-02 | 2018-10-26 | 60000 | 60000 | 60000 | SI MASS (MECH)
Project Name 291 | Project Number291 | Project Manager291 | Program Manager291 | Completion | Location291 | VI | Contact291 | FALSE | 257 |  | 2018-11-01 |  | 2018-11-18 |  | 2018-10-30 | 2018-11-18 | 2018-11-14 | 90000 | 90000 |  | LM Field Mech
Project Name 292 | Project Number292 | Project Manager292 | Program Manager292 | Completion | Location292 | SI | Contact292 | TRUE |  |  | 2018-09-25 |  | 2018-11-02 |  | 2018-09-25 | 2018-11-02 | 2018-10-17 | 108000 | 133000 | 133000 | SI MASS (MECH)
Project Name 293 | Project Number293 | Project Manager293 | Program Manager293 | Completion | Location293 | SI | Contact293 | TRUE | 300 |  | 2018-11-05 |  | 2018-11-16 | 2018-11-05 | 2018-11-05 | 2018-11-16 | 2018-11-16 | 76000 | 76000 |  | SI MASS (SS)
Project Name 294 | Project Number294 | Project Manager294 | Program Manager294 | Completion | Location294 | SI | Contact294 | TRUE |  |  | 2018-09-17 |  | 2018-11-09 |  | 2018-09-17 | 2018-11-09 | 2018-11-09 | 417000 | 490000 |  | SI MASS (SS)
Project Name 295 | Project Number295 | Project Manager295 | Program Manager295 | Completion | Location295 | SI | Contact295 | FALSE | 380 |  | 2018-11-12 |  | 2018-12-05 | 2018-11-12 | 2018-11-12 | 2018-12-05 | 2018-12-05 | 48000 | 48000 |  | SI MASS (SS)
Project Name 296 | Project Number296 | Project Manager296 | Program Manager296 | Completion | Location296 | VI | Contact296 | TRUE |  |  | 2017-10-30 |  | 2017-11-05 |  | 2017-10-30 |  | 2017-11-05 | 12000 |  | 11800 | LM Winders
Project Name 297 | Project Number297 | Project Manager297 | Program Manager297 | Completion | Location297 | VI | Contact297 | TRUE |  | 2018-09-07 | 2018-09-07 | 2018-10-05 | 2018-10-05 |  | 2018-08-16 | 2018-09-04 | 2018-09-04 | 146479 | 146479 | 115324 | LM Winders
Project Name 298 | Project Number298 | Project Manager298 | Program Manager298 | Completion | Location298 | VI | Contact298 | TRUE |  | 2018-08-20 | 2018-08-20 | 2018-09-14 | 2018-09-14 |  | 2018-07-23 | 2018-08-19 | 2018-08-19 | 146479 | 146479 | 115324 | LM Winders
Project Name 299 | Project Number299 | Project Manager299 | Program Manager299 | Completion | Location299 | LM | Contact299 | FALSE |  |  | 2018-10-01 |  | 2018-11-15 |  | 2018-10-09 | 2018-11-15 | 2018-12-03 | 152103 | 136764 | 136764 | LM Elect1
Project Name 300 | Project Number300 | Project Manager300 | Program Manager300 | Completion | Location300 | LM | Contact300 | FALSE |  |  | 2018-06-21 |  | 2018-07-03 |  | 2018-06-21 |  | 2018-07-03 | 25726 |  | 17851 | LM Elect1
Project Name 301 | Project Number301 | Project Manager301 | Program Manager301 | Pre-Construction | Location301 | SI | Contact301 | TRUE |  | 2019-09-03 |  | 2019-10-11 | [5 empty] | 0 | 0 |  | SI MASS (SS) | 2019-10-07 | 2019-10-11 | [9 empty] | 200 | SI MASS (MECH) | 2019-09-03 | 2019-10-04 | [9 empty] | 1440
Project Name 302 | Project Number302 | Project Manager302 | Program Manager302 | Completion | Location302 | VI | Contact302 | FALSE |  |  | 2018-11-19 | 2019-01-30 | 2019-01-30 | 2018-11-19 | 2018-11-19 | 2019-01-30 | 2019-01-16 | 142552 | 0 | 0 | VI Civil
Project Name 303 | Project Number303 | Project Manager303 | Program Manager303 | Completion | Location303 | LM | Contact303 | FALSE |  |  | 2014-11-14 |  | 2017-12-01 |  | 2014-11-30 | 2019-02-28 | 2018-04-30 | 8325880 | 13483519 |  | LM Elect2
Project Name 304 | Project Number304 | Project Manager304 | Program Manager304 | Completion | Location304 | LM | Contact304 | FALSE |  |  | 2018-09-03 |  | 2018-10-31 |  | 2018-11-05 | 2018-11-30 | 2018-11-30 | 390000 | 295000 |  | LM Field Mech |  |  | 2018-09-03 | 2018-10-25 | 2018-09-03 | 2018-11-30 | 2018-11-19 | 2018-11-30 |  |  |  | 893 | VI Civil |  |  | 2018-09-03 | 2018-10-25 | 2018-09-03 |  | 2018-11-22 | 2018-11-05 |  |  |  | 615
Project Name 305 | Project Number305 | Project Manager305 | Program Manager305 | Cancelled | Location305 | VI | Contact305 | FALSE |  |  | 2018-09-10 | 2018-10-15 | 2018-10-15 | 2018-11-30 |  | 2018-11-25 |  | 26730 | 0 | 0 | VI Civil
Project Name 306 | Project Number306 | Project Manager306 | Program Manager306 | Completion | Location306 | SI | Contact306 | FALSE |  | 2018-02-26 | 2018-02-26 | 2018-03-16 | 2018-03-16 |  | 2018-02-26 |  | 2018-03-16 | 95222 | 95222 | 87828 | SI Elect
Project Name 307 | Project Number307 | Project Manager307 | Program Manager307 | Completion | Location307 | VI | Contact307 | FALSE |  |  | 2017-10-09 |  | 2017-12-01 |  | 2017-10-09 | 2018-08-01 | 2018-07-26 | 62000 | 109847 |  | VI Elect
Project Name 308 | Project Number308 | Project Manager308 | Program Manager308 | Cancelled | Location308 |  | Contact308 | FALSE | [12 empty] | LM Line
Project Name 309 | Project Number309 | Project Manager309 | Program Manager309 | Completion | Location309 | LM | Contact309 | FALSE |  | 2018-10-01 | 2018-10-10 | 2018-11-30 | 2018-10-22 |  | 2018-10-10 |  | 2018-10-19 | 26434 | 17541 |  | LM Elect2
Project Name 310 | Project Number310 | Project Manager310 | Program Manager310 | Completion | Location310 | LM | Contact310 | TRUE |  | 2018-06-01 | 2018-06-01 | 2018-08-31 | 2018-08-31 |  | 2018-06-01 | 2019-04-30 | 2018-11-16 | 682410 | 663033 | 688120 | LM Elect2
Project Name 311 | Project Number311 | Project Manager311 | Program Manager311 | Completion | Location311 | LM | Contact311 | FALSE |  | 2018-10-01 | 2018-11-30 | 2018-11-30 | 2018-12-14 | 2018-11-30 | 2018-11-30 | 2018-12-14 | 2018-12-14 | 44509 | 38868 |  | LM Elect2
Project Name 312 | Project Number312 | Project Manager312 | Program Manager312 | Completion | Location312 | LM | Contact312 | FALSE |  | 2018-10-01 | 2018-11-30 | 2018-11-01 | 2018-12-15 | 2018-11-30 | 2018-11-30 | 2018-12-15 | 2018-12-14 | 153425 | 145195 |  | LM Elect2
Project Name 313 | Project Number313 | Project Manager313 | Program Manager313 | Completion | Location313 | NI | Contact313 | TRUE |  |  | 2018-02-05 |  | 2018-04-23 |  | 2018-02-05 |  | 2018-04-23 | 159035 |  | 131238 | NI Elect
Project Name 314 | Project Number314 | Project Manager314 | Program Manager314 | Completion | Location314 | NI | Contact314 | TRUE |  |  | 2018-04-23 |  | 2018-09-10 |  | 2018-04-23 | 2018-10-16 | 2018-10-16 | 714435 | 545820 | 545820 | NI Elect
Project Name 315 | Project Number315 | Project Manager315 | Program Manager315 | Completion | Location315 | NI | Contact315 | TRUE | 635 | 2018-09-24 | 2018-09-24 | 2018-10-30 | 2018-10-30 |  | 2018-09-24 | 2018-10-30 | 2018-11-02 | 78409 | 61571 | 61571 | NI Elect
Project Name 316 | Project Number316 | Project Manager316 | Program Manager316 | Completion | Location316 | NI | Contact316 | TRUE |  | 2018-09-05 | 2018-09-05 | 2018-10-12 | 2018-10-12 |  | 2018-09-05 | 2018-10-12 | 2018-10-26 | 142414 | 113423 | 113423 | NI Elect
Project Name 317 | Project Number317 | Project Manager317 | Program Manager317 | Completion | Location317 | NI | Contact317 | TRUE |  |  | 2018-08-27 |  | 2018-10-15 | 2018-10-22 | 2018-10-22 | 2018-11-07 | 2018-11-07 | 341686 | 185000 |  | NI Civil
Project Name 318 | Project Number318 | Project Manager318 | Program Manager318 | Pre-Construction | Location318 | VI | Contact318 | TRUE |  | 2019-08-19 | 2019-08-19 | 2019-11-22 | 2019-11-22 | 2019-08-19 |  | 2019-11-22 |  | 906802 | 906802 |  | VI Line
Project Name 319 | Project Number319 | Project Manager319 | Program Manager319 | Pre-Construction | Location319 | LM | Contact319 | TRUE | 2152.5 | 2019-01-21 |  | 2019-02-01 | [5 empty] | 243418 | 243418 |  | LM Line
Project Name 320 | Project Number320 | Project Manager320 | Program Manager320 | Completion | Location320 | LM | Contact320 | TRUE |  |  |  |  | 2018-05-19 |  | 2018-02-26 | 2018-11-30 | 2018-10-30 | 340000 | 366000 | 362241 | LM Winders
Project Name 321 | Project Number321 | Project Manager321 | Program Manager321 | Completion | Location321 | SI | Contact321 | FALSE |  |  | 2018-06-04 |  | 2018-07-27 |  | 2018-06-04 |  | 2018-07-27 | 40000 | 40000 | 30200 | SI Elect
Project Name 322 | Project Number322 | Project Manager322 | Program Manager322 | Completion | Location322 | SI | Contact322 | FALSE | 900 | 2018-02-05 | 2018-02-05 | 2021-02-23 | 2021-02-23 | 2018-02-05 | 2018-02-05 | 2021-02-23 |  | 269400 | 269400 |  | SI Elect | 2018-02-05 |  | 2018-02-05 |  | 2018-02-05 |  | 2018-02-05 |  | 67350 | 67350 | 57000 | 300 | SI Elect | 2019-01-21 | 2019-02-28 | 2019-01-21 | 2019-02-28 | 2019-01-21 | 2019-02-28 |  |  | 67350 | 67350 |  | 300 | SI Elect | 2019-09-02 | 2019-10-04 | 2019-09-02 | 2019-10-04 | 2019-09-02 | 2019-10-04 |  |  | 67350 | 67350 |  | 300 | SI Elect | 2020-09-01 | 2020-10-02 | [6 empty] | 67350 | 67350 |  | 300
Project Name 323 | Project Number323 | Project Manager323 | Program Manager323 | Completion | Location323 | LM | Contact323 | TRUE |  |  | 2018-08-13 |  | 2018-10-06 | 2018-08-13 | 2018-08-13 | 2018-11-02 | 2018-11-02 | 320962 | 334128 | 341628 | LM Winders
Project Name 324 | Project Number324 | Project Manager324 | Program Manager324 | Completion | Location324 | SI | Contact324 | TRUE |  |  | 2016-08-15 |  | 2018-03-31 |  | 2016-09-15 |  | 2018-10-25 | 8908486 | 10156124 |  | SI Civil
Project Name 325 | Project Number325 | Project Manager325 | Program Manager325 | Completion | Location325 | LM SI | Contact325 | TRUE | 3500 |  | 2018-04-30 |  | 2018-10-31 |  | 2018-05-02 |  | 2018-07-13 | 415001 |  | 268533 | SI Civil
Project Name 326 | Project Number326 | Project Manager326 | Program Manager326 | Completion | Location326 | SI | Contact326 | TRUE |  |  | 2018-05-29 |  | 2018-10-31 |  | 2018-05-29 |  | 2018-10-25 | 892000 | 580000 | 580000 | SI Elect
Project Name 327 | Project Number327 | Project Manager327 | Program Manager327 | Completion | Location327 | SI | Contact327 | TRUE |  |  | 2015-08-24 |  | 2016-10-19 |  | 2015-08-18 |  | 2017-10-27 | 6400000 |  | 6687000 | SI Line
Project Name 328 | Project Number328 | Project Manager328 | Program Manager328 | Completion | Location328 | SI | Contact328 | TRUE |  |  | 2018-02-26 |  | 2018-07-31 |  | 2018-02-26 |  | 2018-07-31 | 413547 | 234000 | 234000 | SI Elect
Project Name 329 | Project Number329 | Project Manager329 | Program Manager329 | Completion | Location329 | NI | Contact329 | TRUE |  |  | 2017-06-26 |  | 2017-11-03 |  | 2017-06-26 | 2018-10-15 | 2018-10-15 | 2837194 | 3275571 |  | NI Civil
Project Name 330 | Project Number330 | Project Manager330 | Program Manager330 | Completion | Location330 | NI | Contact330 | TRUE |  | 2018-08-15 | 2018-08-21 | 2018-09-30 | 2018-09-22 |  | 2018-08-23 | 2018-10-05 | 2018-10-05 | 277551 | 264791 |  | NI Civil
Project Name 331 | Project Number331 | Project Manager331 | Program Manager331 | Completion | Location331 | SI | Contact331 | FALSE |  |  | 2018-04-01 |  | 2019-03-30 |  | 2018-04-01 |  | 2019-03-30 |  |  |  | SI Line
Project Name 332 | Project Number332 | Project Manager332 | Program Manager332 | Completion | Location332 | SI | Contact332 | TRUE |  |  | 2018-03-19 |  | 2018-11-02 |  | 2018-03-19 |  | 2018-10-26 | 383000 | 257000 | 257000 | SI Elect
Project Name 333 | Project Number333 | Project Manager333 | Program Manager333 | Completion | Location333 | VI | Contact333 | FALSE |  |  | 2017-12-11 |  | 2018-01-25 |  | 2017-12-11 |  | 2018-01-26 | 0 | 0 | 0 | VI Civil
Project Name 334 | Project Number334 | Project Manager334 | Program Manager334 | Completion | Location334 | NI | Contact334 | TRUE |  |  | 2017-12-04 |  |  |  | 2017-12-04 |  | 2017-12-07 | 9000 |  | 7500 | NI Winders
Project Name 335 | Project Number335 | Project Manager335 | Program Manager335 | Completion | Location335 | VI | Contact335 | TRUE |  |  | 2017-05-01 |  | 2017-10-30 |  | 2017-05-01 |  | 2018-02-05 | 212000 |  | 113244 | VI Line
Project Name 336 | Project Number336 | Project Manager336 | Program Manager336 | Completion | Location336 | VI | Contact336 | FALSE |  |  | 2017-06-05 |  | 2017-06-30 | 2017-06-05 | 2017-06-05 |  | 2017-07-19 | 245362 | 390000 |  | VI Winders
Project Name 337 | Project Number337 | Project Manager337 | Program Manager337 | Completion | Location337 | SI | Contact337 | TRUE |  | 2018-03-01 | 2018-04-03 |  | 2018-04-27 | 2018-04-09 | 2018-04-09 | 2018-05-18 | 2018-06-01 | 115097 | 115097 |  | SI Civil
Project Name 338 | Project Number338 | Project Manager338 | Program Manager338 | Completion | Location338 | VI | Contact338 | FALSE |  |  | 2017-07-04 |  | 2017-07-29 | 2017-07-04 | 2017-09-05 | 2017-10-06 | 2017-10-30 | 245362 |  | 344064 | VI Winders
Project Name 339 | Project Number339 | Project Manager339 | Program Manager339 | Completion | Location339 | VI | Contact339 | TRUE |  |  | 2018-01-15 |  | 2018-06-01 |  | 2018-01-15 | 2018-10-30 | 2018-10-17 | 898485 |  | 878027 | VI Line
Project Name 340 | Project Number340 | Project Manager340 | Program Manager340 | Completion | Location340 | VI | Contact340 | TRUE |  |  | 2017-05-01 |  | 2018-06-22 |  | 2018-01-16 |  | 2018-08-31 | 833875 |  | 731938 | VI Line
Project Name 341 | Project Number341 | Project Manager341 | Program Manager341 | Completion | Location341 | SI | Contact341 | TRUE |  |  | 2016-08-22 |  | 2016-12-10 |  | 2016-08-22 | 2017-07-31 | 2017-09-14 | 515000 |  | 754418 | SI Civil
Project Name 342 | Project Number342 | Project Manager342 | Program Manager342 | Completion | Location342 | NI | Contact342 | TRUE |  |  | 2017-05-23 |  | 2017-07-17 |  | 2017-07-18 |  | 2017-12-15 | 576429 | 553405 |  | NI Line
Project Name 343 | Project Number343 | Project Manager343 | Program Manager343 | Completion | Location343 | NI | Contact343 | FALSE |  | 2018-07-10 | 2018-06-25 | 2018-08-31 | 2018-07-12 |  | 2018-06-25 |  | 2018-07-25 | 102693 | 170823 |  | NI Civil
Project Name 344 | Project Number344 | Project Manager344 | Program Manager344 | Completion | Location344 | LM | Contact344 | FALSE |  |  | 2017-12-01 |  | 2017-12-31 |  | 2017-12-01 |  | 2017-12-31 | 14000 |  |  | LM Elect2
Project Name 345 | Project Number345 | Project Manager345 | Program Manager345 | Completion | Location345 | NI | Contact345 | TRUE |  |  | 2017-10-02 |  | 2017-12-15 |  | 2017-10-02 | 2018-03-01 | 2018-03-01 | 262356 | 237497 |  | NI Elect
Project Name 346 | Project Number346 | Project Manager346 | Program Manager346 | Completion | Location346 | SI | Contact346 | TRUE |  |  | 2017-11-15 |  | 2018-01-31 |  | 2017-11-15 |  | 2018-06-05 | 192000 |  | 178000 | SI Elect
Project Name 347 | Project Number347 | Project Manager347 | Program Manager347 | Completion | Location347 | NI | Contact347 | TRUE |  |  | 2017-04-03 |  | 2017-08-17 |  | 2017-05-10 |  | 2017-11-30 | 1079761 |  | 873511 | NI Elect
Project Name 348 | Project Number348 | Project Manager348 | Program Manager348 | Completion | Location348 | NI | Contact348 | FALSE |  |  | 2017-05-23 |  | 2017-09-06 |  | 2017-05-30 |  | 2017-08-28 | 880000 | 1032413 |  | NI Mech
Project Name 349 | Project Number349 | Project Manager349 | Program Manager349 | Completion | Location349 | LM | Contact349 | TRUE |  |  | 2016-04-18 |  | 2017-05-08 |  | 2016-04-18 |  | 2017-09-29 | 1613204 |  | 2684256 | LM Elect1
Project Name 350 | Project Number350 | Project Manager350 | Program Manager350 | Completion | Location350 | VI | Contact350 | FALSE |  |  | 2018-06-04 | 2018-06-12 | 2018-06-11 |  | 2018-06-05 |  | 2018-06-11 | 15660 | 0 | 16798 | VI Civil
Project Name 351 | Project Number351 | Project Manager351 | Program Manager351 | Completion | Location351 | VI | Contact351 | FALSE |  |  | 2017-09-15 |  | 2017-09-10 |  | 2017-09-21 |  | 2017-12-13 | 174771 |  | 163450 | VI Elect
Project Name 352 | Project Number352 | Project Manager352 | Program Manager352 | Completion | Location352 | SI | Contact352 | FALSE |  |  | 2017-04-01 |  | 2017-06-30 | 2017-09-26 |  |  | 2017-10-28 | 181880 |  | 123332 | SI Line
Project Name 353 | Project Number353 | Project Manager353 | Program Manager353 | Completion | Location353 | VI | Contact353 | FALSE |  |  | 2018-04-09 |  | 2018-04-23 |  | 2018-04-09 |  | 2018-04-20 |  | 0 | 0 | VI Civil
Project Name 354 | Project Number354 | Project Manager354 | Program Manager354 | Completion | Location354 | SI | Contact354 | FALSE |  |  | 2018-03-26 |  | 2018-07-06 |  | 2018-03-26 |  | 2018-07-06 | 433000 |  | 390000 | SI LM Elect 2
Project Name 355 | Project Number355 | Project Manager355 | Program Manager355 | Completion | Location355 | LM | Contact355 | FALSE |  |  | 2018-04-05 |  | 2018-04-20 |  | 2018-04-05 |  | 2018-04-20 | 61800 |  | 63046 | LM Elect
Project Name 356 | Project Number356 | Project Manager356 | Program Manager356 | Completion | Location356 | NI | Contact356 | TRUE |  | 2018-09-17 | 2018-09-17 | 2018-10-22 |  | 2018-09-17 | 2018-09-20 |  | 2018-10-19 | 179147 |  | 153679 | NI Elect
Project Name 357 | Project Number357 | Project Manager357 | Program Manager357 | Completion | Location357 | VI | Contact357 | FALSE |  |  | 2017-07-17 |  | 2017-08-14 |  | 2017-07-17 |  | 2017-08-18 | 150000 |  |  | VI Civil
Project Name 358 | Project Number358 | Project Manager358 | Program Manager358 | Completion | Location358 | LM | Contact358 | TRUE |  |  | 2018-05-22 |  | 2018-07-17 |  | 2018-06-14 |  | 2018-07-17 | 176000 | 176000 | 176000 | LM Winders
Project Name 359 | Project Number359 | Project Manager359 | Program Manager359 | Completion | Location359 | NI | Contact359 | TRUE |  |  | 2018-01-29 |  | 2018-04-20 |  | 2018-02-19 |  | 2018-04-20 | 189725 | 120565 |  | NI Elect
Project Name 360 | Project Number360 | Project Manager360 | Program Manager360 | Completion | Location360 | VI | Contact360 | FALSE |  |  | 2018-07-15 |  | 2018-09-15 |  | 2018-07-03 |  | 2018-09-13 | 0 | 0 |  | VI Civil
Project Name 361 | Project Number361 | Project Manager361 | Program Manager361 | Completion | Location361 | LM | Contact361 | TRUE |  |  | 2017-10-02 |  | 2017-10-27 |  | 2017-10-02 |  | 2017-10-26 | 238000 | 210000 | 200000 | LM Winders
Project Name 362 | Project Number362 | Project Manager362 | Program Manager362 | Completion | Location362 | VI | Contact362 | FALSE |  |  | 2018-03-20 |  | 2018-05-30 |  | 2018-03-20 |  | 2018-06-01 | 240026 | 141516 |  | VI Line
Project Name 363 | Project Number363 | Project Manager363 | Program Manager363 | Completion | Location363 | VI | Contact363 | FALSE |  |  | 2017-06-26 |  | 2017-08-21 |  | 2017-06-26 |  | 2017-09-15 | 177476 |  | 258268 | VI Civil
Project Name 364 | Project Number364 | Project Manager364 | Program Manager364 | Completion | Location364 | NI | Contact364 | TRUE |  |  | 2017-05-01 |  | 2017-06-30 |  | 2017-06-06 |  | 2017-06-30 | 93540 |  | 93895 | NI Line
Project Name 365 | Project Number365 | Project Manager365 | Program Manager365 | Completion | Location365 | SI | Contact365 | FALSE |  |  | 2018-01-22 |  | 2019-03-31 | 2018-01-29 |  |  | 2018-03-29 | 278882 | 260000 |  | SI Line
Project Name 366 | Project Number366 | Project Manager366 | Program Manager366 | Completion | Location366 | VI | Contact366 | FALSE |  |  | 2016-07-20 |  | 2017-03-15 |  | 2016-06-15 |  | 2018-03-01 | 496084 |  | 1767586 | VI Line
Project Name 367 | Project Number367 | Project Manager367 | Program Manager367 | Completion | Location367 | NI | Contact367 | TRUE |  |  | 2017-10-23 |  | 2017-12-11 |  | 2017-10-30 |  | 2018-03-22 | 291173 | 428994 |  | NI Civil
Project Name 368 | Project Number368 | Project Manager368 | Program Manager368 | Completion | Location368 | NI | Contact368 | FALSE |  |  | 2015-04-01 |  | 2016-06-30 |  | 2015-04-01 |  | 2018-06-30 | 350000 |  | 348900 | NI Elect
Project Name 369 | Project Number369 | Project Manager369 | Program Manager369 | Completion | Location369 | LM | Contact369 | FALSE |  |  | 2016-05-09 |  | 2017-03-31 |  | 2016-05-16 |  | 2018-05-15 | 986346 | 1172981 |  | LM Line
Project Name 370 | Project Number370 | Project Manager370 | Program Manager370 | Completion | Location370 | SI | Contact370 | TRUE |  |  | 2017-06-12 |  | 2017-07-07 |  | 2017-06-26 |  | 2017-10-13 | 276368 |  | 217209 | SI Line
Project Name 371 | Project Number371 | Project Manager371 | Program Manager371 | Completion | Location371 | NI | Contact371 | TRUE |  |  | 2018-05-28 |  | 2018-06-22 |  | 2018-05-28 |  | 2018-06-19 | 235000 | 235000 |  | NI Winders
Project Name 372 | Project Number372 | Project Manager372 | Program Manager372 | Completion | Location372 | NI | Contact372 | TRUE |  | 2018-07-23 | 2018-07-23 | 2018-08-03 | 2018-08-03 |  | 2018-07-23 |  | 2018-08-03 | 76000 | 76000 |  | NI Winders
Project Name 373 | Project Number373 | Project Manager373 | Program Manager373 | Completion | Location373 | LM | Contact373 | FALSE |  |  | 2016-10-01 |  | 2017-03-01 | 2016-11-28 |  |  | 2017-05-22 | 428984 |  | 311229 | LM Elect1
Project Name 374 | Project Number374 | Project Manager374 | Program Manager374 | Completion | Location374 | LM | Contact374 | FALSE |  |  | 2018-03-21 |  | 2018-04-20 |  | 2018-03-21 |  | 2018-05-02 | 54171 |  | 45507 | LM Elect1
Project Name 375 | Project Number375 | Project Manager375 | Program Manager375 | Completion | Location375 | LM | Contact375 | TRUE |  |  | 2018-01-22 |  |  |  | 2018-01-22 |  | 2018-02-14 | 15500 |  | 15000 | LM Winders
Project Name 376 | Project Number376 | Project Manager376 | Program Manager376 | Completion | Location376 | VI | Contact376 | FALSE |  |  | 2017-06-01 |  | 2018-02-01 |  | 2017-06-15 |  | 2018-03-16 | 550000 |  | 631641 | VI Elect
Project Name 377 | Project Number377 | Project Manager377 | Program Manager377 | Completion | Location377 | LM | Contact377 | TRUE |  |  |  |  | 2018-04-01 |  | 2018-03-13 |  | 2018-04-01 | 110000 |  | 49000 | LM Winders
Project Name 378 | Project Number378 | Project Manager378 | Program Manager378 | Completion | Location378 | LM | Contact378 | TRUE |  |  | 2018-01-15 |  | 2018-02-02 |  | 2018-01-15 |  | 2018-02-23 | 60000 |  | 90000 | LM Winders
Project Name 379 | Project Number379 | Project Manager379 | Program Manager379 | Completion | Location379 | LM | Contact379 | FALSE |  |  | 2016-09-12 |  | 2017-05-30 |  | 2016-10-01 |  | 2017-08-26 | 497824 |  | 619728 | LM Elect2
Project Name 380 | Project Number380 | Project Manager380 | Program Manager380 | Completion | Location380 | VI | Contact380 | FALSE |  |  | 2018-03-21 |  | 2018-04-06 |  | 2018-03-21 |  | 2018-04-03 |  | 0 | 0 | VI Civil
Project Name 381 | Project Number381 | Project Manager381 | Program Manager381 | Completion | Location381 | VI | Contact381 | TRUE |  |  | 2017-06-01 |  | 2017-09-22 |  | 2017-09-06 |  | 2018-02-08 | 1340065 |  | 921563 | VI Line
Project Name 382 | Project Number382 | Project Manager382 | Program Manager382 | Completion | Location382 | LM | Contact382 | TRUE |  |  | 2017-11-21 |  | 2017-11-21 |  | 2017-11-21 |  | 2017-11-13 | 33000 |  | 34000 | LM Winders
Project Name 383 | Project Number383 | Project Manager383 | Program Manager383 | Completion | Location383 | SI | Contact383 | FALSE |  |  | 2017-04-01 |  | 2017-10-31 |  | 2017-03-17 |  | 2017-05-12 | 279339 |  | 239245 | SI Line
Project Name 384 | Project Number384 | Project Manager384 | Program Manager384 | Completion | Location384 | VI | Contact384 | TRUE |  |  | 2018-06-04 |  | 2018-06-08 | 2018-06-04 |  |  | 2018-06-27 | 43000 | 43000 |  | VI Line
Project Name 385 | Project Number385 | Project Manager385 | Program Manager385 | Completion | Location385 | LM | Contact385 | FALSE |  |  | 2017-12-06 |  | 2017-12-06 |  | 2017-12-06 |  | 2017-12-06 | 2000 |  |  | LM Elect2
Project Name 386 | Project Number386 | Project Manager386 | Program Manager386 | Completion | Location386 | LM | Contact386 | FALSE |  |  | 2018-01-29 |  | 2018-02-21 |  | 2018-01-29 |  | 2018-02-27 | 104114 | 104114 |  | LM Elect1
Project Name 387 | Project Number387 | Project Manager387 | Program Manager387 | Completion | Location387 | NI | Contact387 | TRUE |  |  | 2017-05-01 |  | 2017-09-20 |  | 2017-05-24 |  | 2017-10-15 | 556982 | 685674 |  | NI Elect
Project Name 388 | Project Number388 | Project Manager388 | Program Manager388 | Completion | Location388 | LM | Contact388 | FALSE |  |  | 2016-05-15 |  | 2017-11-01 |  | 2016-05-15 |  | 2018-05-08 | 551810 |  | 429226 | LM Elect1
Project Name 389 | Project Number389 | Project Manager389 | Program Manager389 | Completion | Location389 | NI | Contact389 | TRUE |  |  | 2017-05-01 |  | 2017-09-20 |  | 2017-05-24 |  | 2018-03-24 | 690649 | 1031775 |  | NI Elect
Project Name 390 | Project Number390 | Project Manager390 | Program Manager390 | Completion | Location390 | LM | Contact390 | TRUE |  |  | 2018-01-29 |  | 2018-02-23 |  | 2018-01-29 |  | 2018-02-23 | 40000 |  | 60000 | LM Winders
Project Name 391 | Project Number391 | Project Manager391 | Program Manager391 | Completion | Location391 | LM | Contact391 | TRUE |  |  | 2017-09-01 |  | 2017-11-01 |  | 2017-08-01 |  | 2017-09-04 | 180619 |  | 143006 | LM Civil
Project Name 392 | Project Number392 | Project Manager392 | Program Manager392 | Completion | Location392 | LM | Contact392 | FALSE |  |  | 2017-07-07 |  | 2017-09-12 |  | 2017-07-07 |  | 2017-09-12 | 288830 |  | 234642 | LM Elect1
Project Name 393 | Project Number393 | Project Manager393 | Program Manager393 | Completion | Location393 | LM | Contact393 | FALSE |  |  | 2018-04-02 |  | 2018-06-29 |  | 2018-04-02 |  | 2018-06-29 | 500000 |  | 507381 | LM Elect1
Project Name 394 | Project Number394 | Project Manager394 | Program Manager394 | Completion | Location394 | LM | Contact394 | FALSE |  |  | 2017-06-01 |  | 2017-12-01 |  | 2017-08-10 |  | 2018-07-27 | 570455 | 428000 |  | LM Elect1
Project Name 395 | Project Number395 | Project Manager395 | Program Manager395 | Completion | Location395 | LM | Contact395 | FALSE |  |  | 2017-03-19 |  | 2017-04-30 |  | 2017-03-19 |  | 2017-05-26 | 239559 |  | 299139 | LM Line
Project Name 396 | Project Number396 | Project Manager396 | Program Manager396 | Completion | Location396 | VI | Contact396 | TRUE |  |  | 2017-07-01 |  | 2017-12-01 |  | 2017-09-07 |  | 2018-02-08 | 774200 |  | 563716 | VI Line
Project Name 397 | Project Number397 | Project Manager397 | Program Manager397 | Completion | Location397 | SI | Contact397 | FALSE |  |  | 2017-06-12 |  | 2017-08-19 |  | 2017-06-12 |  | 2017-08-17 | 99795 |  |  | SI Elect
Project Name 398 | Project Number398 | Project Manager398 | Program Manager398 | Completion | Location398 | VI | Contact398 | TRUE |  |  | 2017-10-15 |  | 2018-03-01 |  | 2018-02-13 |  | 2018-03-16 | 90000 |  | 64558 | VI Elect
Project Name 399 | Project Number399 | Project Manager399 | Program Manager399 | Completion | Location399 | LM | Contact399 | TRUE |  |  | 2018-02-26 |  | 2018-03-20 |  | 2018-02-26 |  | 2018-04-05 | 63000 |  | 52000 | LM Winders
Project Name 400 | Project Number400 | Project Manager400 | Program Manager400 | Completion | Location400 | SI | Contact400 | TRUE |  |  | 2017-01-30 |  | 2017-02-17 |  | 2017-03-03 | 2018-01-01 | 2018-01-12 | 920000 | 860000 |  | SI Elect
Project Name 401 | Project Number401 | Project Manager401 | Program Manager401 | Completion | Location401 | LM | Contact401 | TRUE | [6 empty] | 2018-02-27 |  | 2018-03-02 | 51900 |  | 62000 | LM Winders
Project Name 402 | Project Number402 | Project Manager402 | Program Manager402 | Completion | Location402 | NI | Contact402 | TRUE |  |  | 2016-04-04 |  | 2017-06-26 |  | 2016-04-04 |  | 2017-12-15 | 3753589 | 3917830 |  | NI Elect
Project Name 403 | Project Number403 | Project Manager403 | Program Manager403 | Completion | Location403 | LM | Contact403 | FALSE |  |  | 2017-10-15 |  | 2018-02-01 |  | 2017-10-30 |  | 2018-02-15 | 241308 |  | 192117 | LM Elect1
Project Name 404 | Project Number404 | Project Manager404 | Program Manager404 | Completion | Location404 | LM | Contact404 | TRUE |  |  | 2017-06-01 |  | 2017-12-30 |  | 2016-11-01 |  | 2018-03-30 | 394757 |  | 192279 | LM Elect
Project Name 405 | Project Number405 | Project Manager405 | Program Manager405 | Completion | Location405 | LM | Contact405 | FALSE |  |  | 2016-06-20 |  | 2016-12-20 | 2016-02-22 |  |  | 2017-03-24 |  | 1007048 |  | LM Elect2
Project Name 406 | Project Number406 | Project Manager406 | Program Manager406 | Completion | Location406 | LM | Contact406 | TRUE |  |  | 2015-10-19 |  | 2017-08-03 |  | 2015-10-19 |  | 2017-08-03 | 4438792 |  | 4975699 | LM Civil
Project Name 407 | Project Number407 | Project Manager407 | Program Manager407 | Completion | Location407 | VI | Contact407 | TRUE |  | 2018-07-17 | 2018-04-01 | 2018-06-01 | 2018-07-01 |  | 2018-07-04 | 2018-09-30 | 2018-09-30 | 524506 |  | 446758 | VI Line
Project Name 408 | Project Number408 | Project Manager408 | Program Manager408 | Completion | Location408 | LM | Contact408 | TRUE |  |  | 2017-02-20 |  | 2017-07-30 |  | 2017-06-09 |  | 2017-09-14 | 189369 |  | 150613 | LM Elect1
Project Name 409 | Project Number409 | Project Manager409 | Program Manager409 | Completion | Location409 | NI | Contact409 | FALSE |  |  | 2018-05-03 |  | 2018-07-31 |  | 2018-05-03 |  | 2018-07-29 | 299021 |  | 293605 | NI Elect
Project Name 410 | Project Number410 | Project Manager410 | Program Manager410 | Completion | Location410 | LM | Contact410 | FALSE |  |  | 2017-02-01 |  | 2017-05-30 |  | 2017-06-01 |  | 2018-03-16 | 1391894 | 1822870 |  | LM Line
Project Name 411 | Project Number411 | Project Manager411 | Program Manager411 | Completion | Location411 | LM | Contact411 | TRUE |  |  | 2017-11-01 |  | 2017-12-31 |  | 2018-02-05 | 2018-05-30 | 2018-06-18 | 228021 | 189251 | 190500 | LM Elect1
Project Name 412 | Project Number412 | Project Manager412 | Program Manager412 | Completion | Location412 | NI | Contact412 | TRUE |  |  | 2017-01-09 |  | 2017-04-30 |  | 2017-02-06 |  | 2017-05-30 | 236250 |  | 236250 | NI Elect
Project Name 413 | Project Number413 | Project Manager413 | Program Manager413 | Completion | Location413 | SI | Contact413 | TRUE |  |  | 2017-09-05 |  | 2017-09-22 |  | 2017-10-10 |  | 2018-06-01 | 98713 |  | 110000 | SI Elect
Project Name 414 | Project Number414 | Project Manager414 | Program Manager414 | Completion | Location414 | VI | Contact414 | TRUE |  | 2018-08-01 | 2018-08-01 | 2018-09-30 | 2018-09-30 |  | 2018-08-01 |  | 2018-09-30 | 228153 | 0 | 190000 | VI Line
Project Name 415 | Project Number415 | Project Manager415 | Program Manager415 | Completion | Location415 |  | Contact415 | FALSE |  |  | 2017-04-24 |  | 2017-05-23 |  | 2017-04-24 | 2017-08-25 | 2017-08-25 | 183829 | 183829
Project Name 416 | Project Number416 | Project Manager416 | Program Manager416 | Completion | Location416 | NI | Contact416 | TRUE |  |  | 2017-08-22 |  | 2018-04-06 |  | 2017-08-22 | 2018-04-06 | 2018-04-06 | 751029 | 730475 | 730475 | NI Elect
Project Name 417 | Project Number417 | Project Manager417 | Program Manager417 | Completion | Location417 | VI | Contact417 | FALSE |  |  | 2017-03-12 |  |  |  | 2017-03-12 |  | 2017-09-10 | 335000 |  | 302319 | VI Elect
Project Name 418 | Project Number418 | Project Manager418 | Program Manager418 | Completion | Location418 | LM | Contact418 | TRUE |  | 2018-06-12 | 2018-06-12 |  | 2018-06-22 |  |  |  | 2018-06-28 | 65733 |  | 57232 | LM civil
Project Name 419 | Project Number419 | Project Manager419 | Program Manager419 | Completion | Location419 | VI | Contact419 | FALSE |  |  | 2017-06-01 |  |  |  | 2017-07-01 |  | 2018-05-25 | 263250 |  | 141184 | VI Elect
Project Name 420 | Project Number420 | Project Manager420 | Program Manager420 | Completion | Location420 | LM | Contact420 | FALSE |  |  | 2017-07-02 |  | 2017-08-31 |  | 2017-09-25 |  | 2018-07-02 | 745886 |  | 978478 | LM Line
Project Name 421 | Project Number421 | Project Manager421 | Program Manager421 | Completion | Location421 | NI | Contact421 | TRUE |  |  | 2018-02-05 |  | 2018-05-31 |  | 2018-04-05 |  | 2018-07-27 | 220975 | 0 | 211711 | NI Civil
Project Name 422 | Project Number422 | Project Manager422 | Program Manager422 | Completion | Location422 | LM | Contact422 | TRUE |  |  | 2018-07-16 |  | 2018-08-10 |  | 2018-07-16 |  | 2018-08-10 | 224327 |  | 153426 | LM civil
Project Name 423 | Project Number423 | Project Manager423 | Program Manager423 | Completion | Location423 | NI | Contact423 | TRUE | [6 empty] | 2017-09-19 |  | 2017-12-22 | 695815 | 835000 |  | NI Line
Project Name 424 | Project Number424 | Project Manager424 | Program Manager424 | Completion | Location424 | NI | Contact424 | FALSE |  |  | 2018-09-03 |  | 2018-09-14 |  | 2018-09-10 |  | 2018-09-14 |  |  |  | NI Civil
Project Name 425 | Project Number425 | Project Manager425 | Program Manager425 | Completion | Location425 | NI | Contact425 | TRUE |  |  | 2016-05-31 |  | 2016-12-07 |  | 2016-05-31 |  | 2017-06-01 | 1658000 |  | 1707979 | NI Elect
Project Name 426 | Project Number426 | Project Manager426 | Program Manager426 | Completion | Location426 | VI | Contact426 | FALSE |  |  | 2016-01-11 |  | 2017-03-11 |  | 2016-01-11 |  | 2017-09-25 | 1140511 |  | 1220002 | VI Elect
Project Name 427 | Project Number427 | Project Manager427 | Program Manager427 | Completion | Location427 | SI | Contact427 | TRUE |  |  | 2017-06-01 |  | 2017-12-15 |  | 2017-10-10 |  | 2018-05-13 | 1273013 |  | 832490 | SI Line
Project Name 428 | Project Number428 | Project Manager428 | Program Manager428 | Completion | Location428 | NI | Contact428 | TRUE |  |  | 2018-01-22 |  | 2018-07-15 |  | 2018-01-22 |  | 2018-07-15 | 998960 | 0 | 843296 | NI Line
Project Name 429 | Project Number429 | Project Manager429 | Program Manager429 | Completion | Location429 | LM | Contact429 | FALSE |  |  | 2018-02-05 |  | 2018-02-19 |  | 2018-02-05 |  | 2018-02-13 | 96659 | 96659 |  | LM Warehouse
Project Name 430 | Project Number430 | Project Manager430 | Program Manager430 | Completion | Location430 | VI | Contact430 | FALSE |  |  | 2017-04-15 |  | 2017-09-15 |  | 2017-04-15 |  | 2017-08-08 | 9749662 |  |  | VI Elect
Project Name 431 | Project Number431 | Project Manager431 | Program Manager431 | Completion | Location431 | VI | Contact431 | TRUE |  |  | 2017-12-10 |  | 2018-03-31 |  | 2018-01-16 |  | 2018-05-01 | 200000 | 142983 |  | VI Elect
Project Name 432 | Project Number432 | Project Manager432 | Program Manager432 | Completion | Location432 | SI | Contact432 | TRUE |  | 2018-05-01 | 2018-05-07 |  | 2018-05-27 |  | 2018-05-18 |  | 2018-06-07 | 70000 | 0 |  | SI Elect
Project Name 433 | Project Number433 | Project Manager433 | Program Manager433 | Completion | Location433 | LM | Contact433 | FALSE |  |  | 2018-03-09 |  | 2018-03-31 |  | 2018-03-09 |  | 2018-05-18 | 37022 |  | 57685 | LM Elect1
Project Name 434 | Project Number434 | Project Manager434 | Program Manager434 | Completion | Location434 | LM | Contact434 | TRUE |  |  | 2017-09-01 |  | 2017-10-31 |  | 2017-09-25 | 2018-04-15 | 2018-04-13 | 313219 | 357114 | 351970 | LM Elect1
Project Name 435 | Project Number435 | Project Manager435 | Program Manager435 | Completion | Location435 | LM | Contact435 | FALSE |  |  | 2018-05-22 |  | 2018-06-01 |  | 2018-05-22 |  | 2018-06-01 | 38411 |  | 39033 | LM Elect1
Project Name 436 | Project Number436 | Project Manager436 | Program Manager436 | Completion | Location436 | NI | Contact436 | FALSE |  |  | 2017-06-19 |  | 2017-08-31 |  | 2017-08-22 |  | 2018-02-22 | 229448 | 283480 |  | NI Line
Project Name 437 | Project Number437 | Project Manager437 | Program Manager437 | Completion | Location437 | NI | Contact437 | TRUE |  | 2018-04-17 | 2018-04-18 | 2018-05-04 |  |  | 2018-04-18 |  | 2018-05-04 | 272059 | 0 | 212939 | NI Line
Project Name 438 | Project Number438 | Project Manager438 | Program Manager438 | Completion | Location438 | LM | Contact438 | FALSE |  |  | 2016-03-11 |  | 2016-06-16 | 2016-03-11 |  | 2016-11-30 |  |  | 499364 |  | LM Elect1
Project Name 439 | Project Number439 | Project Manager439 | Program Manager439 | Completion | Location439 | LM | Contact439 | TRUE |  |  | 2018-02-19 |  | 2018-05-03 |  | 2018-04-09 |  | 2018-04-27 | 63000 |  | 50000 | LM Winders
Project Name 440 | Project Number440 | Project Manager440 | Program Manager440 | Completion | Location440 | LM | Contact440 | FALSE |  |  | 2018-03-30 |  | 2018-04-15 |  | 2018-03-30 |  | 2018-04-15 | 112000 |  | 86195 | LM Mech
Project Name 441 | Project Number441 | Project Manager441 | Program Manager441 | Completion | Location441 | LM | Contact441 | TRUE |  |  | 2016-06-01 |  | 2016-12-01 |  | 2016-06-01 |  | 2017-08-31 | 1746170 |  | 2395400 | LM Elect1
Project Name 442 | Project Number442 | Project Manager442 | Program Manager442 | Completion | Location442 | LM | Contact442 | FALSE |  |  | 2016-05-18 |  | 2017-08-31 |  | 2016-05-18 |  | 2017-08-31 |  | 255026 |  | LM Elect1
Project Name 443 | Project Number443 | Project Manager443 | Program Manager443 | Completion | Location443 | NI | Contact443 | TRUE |  |  | 2015-08-17 |  | 2017-05-25 |  | 2015-10-16 |  | 2017-11-27 | 2863875 | 3660181 |  | NI Elect
Project Name 444 | Project Number444 | Project Manager444 | Program Manager444 | Completion | Location444 | NI | Contact444 | TRUE |  |  | 2016-08-17 |  | 2017-07-20 |  | 2016-08-08 |  | 2018-04-13 | 665293 | 724723 |  | NI Line
Project Name 445 | Project Number445 | Project Manager445 | Program Manager445 | Completion | Location445 | LM | Contact445 | FALSE |  |  | 2017-06-01 |  | 2017-08-30 |  | 2017-05-04 |  | 2018-06-15 | 1015814 |  | 1140599 | LM Elect1
Project Name 446 | Project Number446 | Project Manager446 | Program Manager446 | Completion | Location446 | LM | Contact446 | TRUE |  |  | 2018-09-10 |  | 2018-10-05 |  | 2018-09-10 |  | 2018-10-04 | 97874 |  | 87982 | LM civil
Project Name 447 | Project Number447 | Project Manager447 | Program Manager447 | Completion | Location447 | LM | Contact447 | FALSE |  |  | 2018-03-15 |  | 2018-03-30 |  | 2018-03-15 |  | 2018-03-30 | 95100 |  | 86610 | LM Elect1
Project Name 448 | Project Number448 | Project Manager448 | Program Manager448 | Completion | Location448 | LM | Contact448 | FALSE |  |  | 2015-05-11 |  | 2016-06-01 |  | 2015-05-11 | 2018-03-15 | 2018-02-27 | 294445 |  |  | LM Elect1
Project Name 449 | Project Number449 | Project Manager449 | Program Manager449 | Completion | Location449 | NI | Contact449 | TRUE |  |  | 2017-09-11 |  | 2018-12-05 |  | 2018-03-05 |  | 2018-07-01 | 424182 |  | 516527 | NI Elect
Project Name 450 | Project Number450 | Project Manager450 | Program Manager450 | Completion | Location450 | LM | Contact450 | FALSE |  |  | 2015-11-01 |  | 2015-11-20 | 2016-07-15 |  |  | 2017-04-14 | 487627 |  | 542231 | LM Civil
Project Name 451 | Project Number451 | Project Manager451 | Program Manager451 | Completion | Location451 | LM | Contact451 | TRUE |  |  | 2016-06-07 |  | 2016-07-29 |  | 2016-10-01 |  | 2016-07-23 | 927000 |  | 1090166 | LM Line
Project Name 452 | Project Number452 | Project Manager452 | Program Manager452 | Completion | Location452 | LM | Contact452 | TRUE |  |  | 2017-12-01 |  | 2018-04-01 |  | 2018-01-04 |  | 2018-03-28 | 410000 |  | 313977 | LM Elect
Project Name 453 | Project Number453 | Project Manager453 | Program Manager453 | Completion | Location453 | VI | Contact453 | FALSE |  |  | 2016-06-20 |  | 2016-12-16 |  | 2016-06-15 |  | 2017-06-23 | 3794510 |  | 3572547 | VI Line
Project Name 454 | Project Number454 | Project Manager454 | Program Manager454 | Completion | Location454 | SI | Contact454 | FALSE |  | 2018-05-01 |  |  | 2018-06-30 | 2018-05-14 | 2018-05-14 |  | 2018-05-30 | 150000 |  | 125420 | SI Line
Project Name 455 | Project Number455 | Project Manager455 | Program Manager455 | Completion | Location455 | LM | Contact455 | TRUE |  |  | 2018-02-23 |  | 2018-03-09 |  | 2018-02-23 |  | 2018-03-09 | 26279 |  | 25985 | LM Civil
Project Name 456 | Project Number456 | Project Manager456 | Program Manager456 | Completion | Location456 | SI | Contact456 | FALSE |  |  | 2017-01-01 |  | 2017-11-30 |  | 2016-11-07 |  | 2017-11-30 | 1647000 |  | 1207000 | SI Elect
Project Name 457 | Project Number457 | Project Manager457 | Program Manager457 | Completion | Location457 | SI | Contact457 | FALSE |  |  | 2017-05-01 |  | 2017-10-31 |  | 2017-05-15 |  | 2017-10-31 | 232000 |  | 408000 | SI Civil
Project Name 458 | Project Number458 | Project Manager458 | Program Manager458 | Completion | Location458 | SI | Contact458 | FALSE |  |  | 2017-03-01 |  | 2017-12-01 |  | 2017-04-03 |  | 2017-12-01 | 427000 |  | 352000 | SI Civil
Project Name 459 | Project Number459 | Project Manager459 | Program Manager459 | Completion | Location459 | NI | Contact459 | FALSE |  |  | 2014-09-25 |  | 2015-08-30 |  | 2014-09-25 |  | 2017-06-21 | 1672830 |  | 1875000 | NI Elect
Project Name 460 | Project Number460 | Project Manager460 | Program Manager460 | Completion | Location460 | VI | Contact460 | FALSE |  |  | 2018-06-21 | 2018-07-09 | 2018-07-09 |  | 2018-06-21 |  | 2018-07-06 | 0 | 0 | 0 | VI Civil
Project Name 461 | Project Number461 | Project Manager461 | Program Manager461 | Completion | Location461 | LM | Contact461 | FALSE |  |  | 2018-01-08 |  | 2018-01-09 |  | 2018-01-08 |  | 2018-01-09 | 5000 |  |  | LM Elect2
Project Name 462 | Project Number462 | Project Manager462 | Program Manager462 | Completion | Location462 | LM | Contact462 | TRUE |  |  | 2018-03-05 |  | 2018-04-14 |  | 2018-03-05 |  | 2018-04-14 | 211000 |  | 200000 | LM Winders
Project Name 463 | Project Number463 | Project Manager463 | Program Manager463 | Completion | Location463 | LM | Contact463 | TRUE |  |  | 2017-11-20 |  | 2018-02-23 |  | 2017-11-20 |  | 2018-02-23 | 205000 |  | 203000 | LM Winders
Project Name 464 | Project Number464 | Project Manager464 | Program Manager464 | Completion | Location464 | LM | Contact464 | FALSE |  |  | 2017-10-16 |  | 2017-10-21 |  | 2017-10-20 |  | 2017-11-30 |  |  | 284000 | LM Mech
Project Name 465 | Project Number465 | Project Manager465 | Program Manager465 | Completion | Location465 | SI | Contact465 | TRUE |  |  | 2017-04-01 |  | 2018-10-30 |  | 2017-10-13 |  | 2018-10-05 | 2250000 | 2167230 |  | SI Line
Project Name 466 | Project Number466 | Project Manager466 | Program Manager466 | Completion | Location466 | SI | Contact466 | TRUE |  |  | 2018-02-26 |  | 2018-07-31 |  | 2018-02-26 |  | 2018-08-01 | 259421 | 176933 |  | SI Elect
Project Name 467 | Project Number467 | Project Manager467 | Program Manager467 | Completion | Location467 | VI | Contact467 | FALSE |  |  | 2018-09-10 |  | 2018-10-08 |  | 2018-09-18 |  | 2018-10-08 | 78183 | 0 | 0 | VI Civil